## Data Elements (hidden)
Component | Scope Type | State/Country | Funding | Program | Construction Classifications
USAF | SM | AL | SC | Commissary | Administrative Office/Supply Center
USA | SF | AK | NAF | Exchange | Aquatic Training Facility/Bathhouse for military training, physical fitness, combat training and/or therapy
USN | Bays | AZ | PF | Lodging | Auditorium/Multipurpose Theater
USMC | Cabins | AR | APF | MWR | Gymnasium/Fieldhouse/Physical Activities
| Connection | CA |  | Privately Financed | Library
| Cottages | CO |  |  | Playing Courts and Fields (associated with physical conditioning)
| Each | CT |  |  | Recreation Center/Day Room/Multipurpose Recreational Facility (Military Personnel)
| Holes | DE |  |  | Park and Picnic Areas
| Islands | FL |  |  | Military and Family Assistance Centers
| Lanes | GA |  |  | Arts and Crafts/Skill Development
| Pads | HI |  |  | Automotive Skill Development Center
| Pumps | ID |  |  | Campgrounds
| Rooms | IL |  |  | Outdoor Recreation Pavilion
| Sites | IN |  |  | Playing Courts and Fields
| Slips | IA |  |  | Recreation Equipment Issue/Checkout Facility
| Spaces | KS |  |  | Recreation Swimming Pools/Bathhouse/Aquatic Centers
| Units | KY |  |  | Youth Centers/Courts/Playing Fields – OCONUS
| Well | LA |  |  | Youth Centers/Courts/Playing Fields – CONUS
|  | ME |  |  | Bowling Centers (16 lanes or less)
|  | MD |  |  | Child Development Centers
|  | MA |  |  | Marinas without Resale or Private Berthing
|  | MI |  |  | Information, Tickets and Tours Facilities
|  | MN |  |  | Service Member Techno-Activites Center
|  | MS |  |  | Community Activity and Recreation Centers (Military and Family Members)
|  | MO |  |  | Aero Club
|  | MT |  |  | Amateur Radio Facility
|  | NE |  |  | Joint Service and Military Service Recreation Centers (accommodations/dining and resale facilities)
|  | NV |  |  | Bandstand
|  | NH |  |  | Bathhouse
|  | NJ |  |  | Bowling Centers (more than 16 lanes)
|  | NM |  |  | Car Wash
|  | NY |  |  | Golf Course/Facility
|  | NC |  |  | Marinas/Boathouse/Watercraft Storage
|  | ND |  |  | Open Messes/Military Clubs/Food and Beverage
|  | OH |  |  | Other MWR Resale Outlets
|  | OK |  |  | Outdoor Theater
|  | OR |  |  | Recreational Lodging
|  | PA |  |  | Recreational Water Parks
|  | PR |  |  | Riding Stable
|  | RI |  |  | Rod and Gun Club
|  | SC |  |  | Recreational Vehicle (RV) Parks and Storage Lots
|  | SD |  |  | Skating Rink (Ice or Roller)
|  | TN |  |  | Open Messes/Military Clubs/Food and Beverage
|  | TX |  |  | Other MWR Resale Outlets
|  | UT |  |  | Outdoor Theater
|  | VT |  |  | Recreational Lodging
|  | VA |  |  | Recreational Water Parks
|  | WA |  |  | Riding Stable
|  | WV |  |  | Rod and Gun Club
|  | WI |  |  | Recreational Vehicle (RV) Parks and Storage Lots
|  | WY |  |  | Skating Rink (Ice or Roller)
|  | Afghanistan |  |  | PCS Lodging Facility (in support of official PCS travel, operated as MWR Category C)
|  | Bahrain |  |  | Equipment Rental
|  | Belgium |  |  | Animal Kennels and Care
|  | Cuba |  |  | Exchange Logistical, Administrative, Storage and Maintenance Facilities outside the United States
|  | Djibouti |  |  | Exchange Facilities required in areas of military conflict, wartime deployments, and in support of contingency, humanitarian, and peacekeeping operations
|  | Germany |  |  | Exchange Facilities required as integral parts of air terminal, hospital, housing, or other MILCON projects
|  | Greece |  |  | Exchange operated laundries and dry cleaning plants, bakeries, dairies, or similar facilities in support of a military mission, wartime deployments, and in support of contingency, humanitarian, and peacekeeping operations
|  | Greenland |  |  | Retail Stores, Malls, and Shopping Centers
|  | Guam |  |  | Convenience Stores
|  | Honduras |  |  | Automotive repair, gas, and service stations
|  | Iraq |  |  | Packaged beverage stores
|  | Italy |  |  | Laundry and dry cleaning
|  | Japan |  |  | Self-storage
|  | Korea, Republic of |  |  | Name Brand Fast Food
|  | Kuwait |  |  | All Other Exchange Facilities
|  | Marshall Islands |  |  | Exchange Category C – All Facilities
|  | Netherlands |  |  | Category A – TDY Lodging Facility (in support of official TDY travel)
|  | Norway |  |  | Category A – PCS Lodging Facility (in support of official PCS travel)
|  | Portugal |  |  | Category B – Stars & Stripes Facilities
|  | Qatar |  |  | Special Purpose Funds: Category C – All Facilities
|  | Romania |  |  | Commissary Store
|  | Saudi Arabia |  |  | Commissary Administrative Offices
|  | Singapore |  |  | Commissary Central Product Processing
|  | Spain |  |  | Banks
|  | Turkey |  |  | Credit Unions
|  | United Arab Emirates |  |  | Family Assistance Centers
|  | United Kingdom |  |  | Museums
Monuments and Museums
Service Academy Extra-Curricular Activities
Thrift Shop
Supplemental Mission Funds: Category C – All Facilities

## Tab Instructions
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
Tab Instructions
Tab Instructions
Tab | Instructions
Tab Instructions | A supplementary list of instructions and information on each of the NAF Construction Workbook tabs.
Data Definitions | A supplementary list of all terms and definitions used in NAF Construction Workbook.
(0) NAFSGL Installation List | A supplementary list of all Installations, Installation Codes, Service, State/Territory, Country for Component reference.
(1) Major Const Proj Sum Data | The Major Construction projects shall be summarized by program, showing State/Country, Installation, Project Title, Service, Total Investment Cost, Construction Cost, Design Cost, Collateral Equipment cost, Design stage, Net Present Value, Internal Rate of Return, Payback Period, Scope, Estimated Contract Award date, and Funding Source.
(2) Major Proj Req Waivers | A summary listing of policy waivers for DoW NAF, Commissary Surcharge, and Privately Financed NAF Construction projects.
(3) Minor Const Proj Sum Data | Summary of Minor Construction projects approved since the last report to the Congress shall be provided, specifying State/Country, Installation, Project Title, Service, Total Investment Cost, Construction Cost, Design Cost, Collateral Equipment Cost, Scope, Estimated Contract Award Date, and the Funding Source (surcharge, NAF, or private funds).
(4) Cancelled Const Proj Sum | List previously approved Major Construction projects cancelled since the last report. Specify the Fiscal Year Approved, State/Country, Installation, Project Title, Service, and Total Investment Cost. A summary paragraph shall be provided describing the rationale for each canceled project.
(5) Delayed Contract Award Sum | List previously approved projects for which contracts have not been awarded within 1 fiscal year following the approved program year. The list shall provide Fiscal Year Approved, State/Country, Installation, Project Title, Service, Total Investment Cost, and Estimated Contract Award Date, and Rationale for Delay.
(6) Cost and Scope Change | List previously approved Major and Minor Construction projects that require USD(P&R) approval and congressional notification due to an increase of the Construction Cost or a change in Scope. The list shall provide Fiscal Year Approved, State/Country, Installation, Project Title, Service, Approved Total Investment Cost and Scope, and new Total Investment Cost and Scope. Individual project documentation, supporting each project and rationale for the change in Scope is required. The threshold for reporting a change in Construction Cost is set at 25% and the threshold for reporting a change in Scope is set at 10%.
(7) MILCON | A summary list of NAF Construction projects submitted in the coinciding President's Budget Request for Military Construction appropriations shall be provided and include the location by State/County, Installation, Project Title, Service, and Construction Cost.
(8) Public-Private Ventures | A summary list of proposed PPV projects anticipated for Contract Award during the upcoming Fiscal Year shall be provided and include the location by State/County, Installation, Project Title, Service, and Projected Savings.
(9) Enhanced Use Lease Summary | A list of enhanced use lease agreements between the Military Department and another party for the lease of DoW real property pursuant to Section 2667 of Title 10, U.S.C. that includes the provision of in-kind consideration executed in the previous year will be submitted as part of the annual reporting requirement.
(10) Status of Major Projects | A list of the status of previously Approved Major Construction Projects that are ongoing or have been completed since the last report to the Department of War and the Congress. The list shall provide Fiscal Year Approved, State/Country, Installation, Project Title, Service, Initial DoW Approved Total Investment Cost, current DoW Approved Total Investment Cost, Initial DoW Approved Project Scope, Current DoW Approved Project Scope, Actual Total Investment Cost, Completion Date, Funding Source, and Date Post Validation Assessment was completed.
(11) PY2027 Capital Investment | The Capital Investment program will include a summary of investment in the DoW NAF, Commissary Surcharge, and Privately Financed tangible fixed assets. This program summary includes the obligations of Commissary Surcharge funds for Capital Assets, Capital Expenditures, and Contractual Commitments for NAF tangible fixed assets. The report will include the actual acquisition cost of NAF tangible fixed assets, and the obligations incurred for Commissary Surcharge fund Capital Assets for the 2 prior year actual amounts, the Current Year Budget amount, the Program Year, and the Program Year plus 1 year. The reported NAF Capital Expenditures will exclude those NAF Expenditures offset by appropriations received under the DoW MWR Utilization Support and Accountability and Uniform Funding and Management practices. Further information on Utilization Support and Accountability and Uniform Funding and Management practices is included in DoWI 1015.15.
(12) 5 Year Funding Report | A 5-year strategic recapitalization plan. NAF Construction planning must consider the strategic goals and missions of these activities in support of the personnel and readiness program. The 5-year strategic recapitalization plan will: 1. Include Major and Minor Construction, Information Technology, Furniture, Fixtures, Equipment, and other planned Capital Investments. 2. Document all Construction program Funding Sources: APF, NAF, CS, and PF.

## Data Definitions
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
Data Definitions Tab
Data Definitions for the Construction Workbook
Metric | Definition
Actual Completion Date | The actual date on which the reported project was completed.
Actual Date Post Occupancy Review Completed | The actual date on which the reported project's Post Occupancy Review was completed.
Approved Construction Cost | The approved direct cost for labor, material, installed equipment integral to the facility, supervision, inspection and overhead, and profit required in order to construct a facility. It includes Design Costs when part of a Design/Build Construction contract. It does not include Design Costs prior to Construction Contract Award or the cost of collateral equipment.
Approved Cost Scope | The approved defined boundaries of the project in specified metric units, the project's measurable size either in the form of its dimension, or other quantifying unit of measure.
Approved Cost Scope Type | The approved metric units used to define a project's measurable size.
Cat (A,B,C) | The category relevant to the program related to the reported project.
Commissary Surcharge Fund Capital Assets | Includes Capital Assets acquired with Commissary Surcharge Funds. Volume 1, Appendix A of reference (g) defines Capital Assets as obligations for the purchase of equipment (furniture and fixtures, machinery, automated data processing and telecommunication equipment), land, and structures.
Commissary Surcharge Funds (CS) | In accordance with section 2685(d) of 10 U.S.C. (reference (h)), funds originating from the adjustment of sales prices of goods and services sold in commissary store facilities. These funds shall be used only to acquire (including acquisition by lease), construct, convert, expand, improve, repair, maintain, and equip the physical infrastructure of commissary stores and central product processing facilities of the defense commissary system; and to cover environmental evaluation and construction costs, including surveys, administration, overhead, planning, and design, related to activities described in this definition. The term "physical infrastructure" includes real property, utilities, and equipment (installed and free standing and including computer equipment), necessary to provide a complete and usable commissary store or central product processing facility.
Completed Project | Any project that is completed since the previous annual report.
Completion Date | The date where no more Design, Construction, or Collateral Equipment costs paid with NAF or Commissary Surcharge Funds will be incurred by the project, but some SIOH or PCAS may still be incurred.
Component | The Military Service who is benefitting from the reported project (e.g., Air Force, Army, Marine Corps, Navy).
Construction Cost | The direct cost for labor, material, installed equipment integral to the facility, supervision, inspection and overhead, and profit required in order to construct a facility. It includes Design Costs when part of a Design/Build construction contract. It does not include Design Costs prior to Construction Contract Award or the cost of collateral equipment.
Contract Award Date | The official date when a contract is formally granted to the reported project, marking the start of agreed contractual obligations or activities.
Cost & Scope Threshold | For Major Projects previously approved by the USD(P&R) the Construction Cost shall not be exceeded by more than 25 percent or the scope changed by more than 10 percent without approval by the USD(P&R) and reporting to the Congress.
Country | The country where the reported project is located.
Current Approved Project Scope | As of the date the report is submitted, the boundaries of the project by specifying in metric units, the project's measurable size either in the form of its dimensions or other quantifying unit of measure.
Current Approved Project Scope Type | As of the date the report is submitted, the metric units used to define a project's measurable size.
Current Approved Total Investment | As of the date the report is submitted, the sum of all Design, Construction, SIOH, PCAS, and collateral equipment costs paid with NAF or Commissary Surcharge Funds.
Design | Drawings and other documents illustrating the scale and relationship of the features, functions and characteristics of the project to include material qualities and properties.
Design Cost | Costs associated to drawings and other documents illustrating the scale and relationship of the features, functions and characteristics of the project to include material qualities and properties.
Design Stage | The stage of the project in which drawings and other documents illustrating the scale and relationship of the features, functions and characteristics of the project to include material qualities and properties are created.
Design/Build | A contracting method in which the Design and Construction are combined in a single contract with one contractor.
Design/Build, Turnkey, or Design/Bid/Build | The contracting or procurement method most relevant to the reported project.
DoW Facility Analysis Categories (FAC) Code (4-digit) | The established high-level facility categorization that groups facilities with similar functions and units of measure from each Military Department and Washington Headquarters Services. DoW FAC Codes are represented by 4-digits.
Equipment Cost | All expenses associated with the acquisition, use, operation, and maintenance of machinery, vehicles, and tools necessary for completing a project.
Estimated Contract Award Date | The estimated date of when a contract is formally granted to the reported project, marking the start of agreed contractual obligations or activities.
Estimated Outstanding Total Investment Cost | The difference between the Projected Total Investment Cost and the Total Investment to Date at the time of reporting. For example, if the Projected Total Investment Cost for a project is $3,000 and the Total Investment Cost to Date is $2,500, the Estimated Outstanding Total Investment Cost would be $500. This term was named "Estimated Total Cost to Completion" to previous NAF Construction Program Workbooks.
Expected Completion Date | The theoretical date by which a project is anticipated to be finished, based on current plans or schedules.
Fifteen Percent (15%) Design | That point in the design process where the site and utilities plans, schematic floor plan, and all major building systems are identified in sufficient detail to provide a reasonable estimate of the cost of the project.
Fiscal Year (FY) Approved | The Fiscal Year in which the appropriate approvals have been processed for a project, enabling the pursuit of a Contract Award.
Funding | The type of funding used to fund a project (NAF, Privately Financed, Commissary Surcharge).
Information Provider | The organization which reports on the projects and submits the report (e.g., AAFES, Air Force, Army, DeCA, Marine Corps, Navy, NEXCOM).
Initial Approved Project Scope | Once the project has been approved, the boundaries of the project by specifying in metric units, the project's measurable size either in the form of its dimensions or other quantifying unit of measure.
Initial Approved Project Scope Type | Once the project has been approved, the metric units used to define a project's measurable size.
Initial Approved Total Investment | Once the project has been approved, the sum of all Design, Construction, SIOH, PCAS, and collateral equipment costs paid with NAF or Commissary Surcharge Funds.
Installation Code | Code associated with the installation relevant to the reported project.
Installation Name | Name of the installation relevant to the reported project.
IRR | The annual rate of growth that an investment is expected to generate. The IRR is a metric used in financial analysis to estimate the profitability of a potential investment. The IRR is the discount rate that makes the NPV of all cash flows equal to zero in a discounted cash flow analysis. It is calculated by taking the difference between the current or expected value and original value divided by the original value and multiplied by 100.
Leasing Entity | Entity from whom the Enhanced Use Lease was procured from for a reported project.
Major Construction Project | A Construction project with a Construction Component Cost that exceeds $4,000,000.
Military Construction (MILCON) | Any Construction, development, conversion, or extension of any kind carried out with respect to a military installation authorized by and financed with appropriations made available by the Congress.
Minor Construction Project | A Construction project with a Construction Component Cost between $2,000,000 and $4,000,000.
New Construction Cost | The new direct cost for labor, material, installed equipment integral to the facility, supervision, inspection and overhead, and profit required in order to construct a facility. It includes Design Costs when part of a Design/Build Construction Contract. It does not include design costs prior to Construction Contract Award or the cost of collateral equipment.
New Construction Scope | The new defined boundaries of the project in specified metric units, the project's measurable size either in the form of its dimension, or other quantifying unit of measure.
New Construction Scope Type | The new metric units used to define a project's measurable size.
NPV | The difference between the present value of cash inflows and the present value of cash outflows over a period of time.
Original Program Year | The Government FY (October 1 through September 30) originally reported that a major construction project is programmed for execution for Construction to begin.
Payback Period | The amount of time it takes for an investment to generate enough cash flows to recover its initial cost, indicating how quickly the investment will be repaid.
Post Occupancy Review (POR) Explanation | For Completed Projects, please fill in any details relevant to the Post Occupancy Review (e.g., when the POR will be completed, the results of the POR, etc.).
Privately Financed (PF) | Funding provided from anon-Federal entity. May include public-private ventures, donations, private funds, and commercial borrowing.
Program | The program relevant to the reported project.
Program Year (PY) | The Government FY (October 1 through September 30) that a Major Construction Project is programmed for execution for Construction to begin.
Project / Cost Avoidance | Theoretical costs that were not incurred due to the Policy Requiring Waiver used.
Project Cost | Includes the Commissary Surcharge, Nonappropriated Fund, or Privately Funded Construction Cost and includes the associated contingency, SIOH, and PCAS costs. In the case of Design-Build contracts, the cost of the Design portion of the Construction Contract is also included. Project Cost does not include collateral equipment costs (e.g., Furnitures, Fixtures, and Equipment).
Project Number | The unique identifying number for the reported NAF Construction project.
Project Title | The title of the project that is being reported.
Projected Total Investment Cost | As of the report submission date, provide the projected final Total Investment Cost to Date at project completion (including all Design, Construction, SIOH, PCAS, and collateral equipment costs funded by NAF or Commissary Surcharge Funds). This figure will be used to compare the Total Investment Cost to Date reported now with the project’s projected final total at completion. For example, if the Projected Total Investment Cost for a project is $3,000 and the Total Investment Cost to Date is $2,500, the Estimated Outstanding Total Investment Cost would be $500. This term was named "Projected Total Cost" to previous NAF Construction Program Workbooks.
Public-Private Venture (PPV) | As defined in reference (c), an agreement between a DoW Nonappropriated Fund instrumentality and a non-Federal entity under which the non-Federal entity provides goods, services, or facilities to authorized MWR and exchange patrons. A non-Federal entity may, through the public-private venture, provide a portion or all of the financing, Design, Construction, collateral equipment, staffing and operation of a program for goods, services, or facilities.
Scope | Defines the boundaries of the project by specifying in metric units, the project's measurable size either in the form of its dimensions or other quantifying unit of measure.
Scope Type | The metric units used to define a project's measurable size.
State/Territory | The state or territory where the reported project is located.
Thirty-Five Percent (35%) Design | The point in the Design Stage that provides ample detail to define scope and detailed cost estimates for consideration in the budgeting process.
Total Investment Cost | The sum of all Design, Construction, SIOH, PCAS, and collateral equipment costs paid with NAF or Commissary Surcharge Funds. This figure includes collateral equipment costs, so this figure should represent a higher value than a project's reported Project Cost, which excludes collateral equipment costs.
Total Investment Cost to Date | As of the date the report is submitted, the sum of all Design, Construction, SIOH, PCAS, and collateral equipment costs paid with NAF or Commissary Surcharge Funds that have been spent to date. This figure includes collateral equipment costs, so this figure should represent a higher value than a project's reported Project Cost, which excludes collateral equipment costs. This term was named "Actual Cost to Date" to previous NAF Construction Program Workbooks.
Total Value | The total value of the Enhanced Use Lease for the reported project.
Turnkey Contracting | A procurement method whereby a single contractor is responsible for the Design and Construction of the facility under one or multiple contracts.

## (0) NAFSGL Installation List
*The Installation List provided in this workbook is sourced from the latest version of the NAFSGL (Version 6.0)
Service | Service Identifier | Installation Code (X XXXX) | Ins Code | Installation Name | State/Territory |  | Country | Feedback & Comments
Air Force | A | 0108 | A0108 | 319th Air Expeditionary Group | Expeditionary | Expeditionary | Not Applicable | Project Number | Installation Name Missing | State/Country | Further Comments
Air Force | A | 0137 | A0137 | 332nd Balad | Expeditionary | Expeditionary | Not Applicable
Air Force | A | 0114 | A0114 | 379th Air Expeditionary Wing | Expeditionary | Expeditionary | Not Applicable
Air Force | A | 0134 | A0134 | 386th Air Expeditionary Wing (Ali Al Salem Air Base) | Expeditionary | Expeditionary | Kuwait
Air Force | A | 0124 | A0124 | 405th Air Expeditionary Wing | Expeditionary | Expeditionary | Not Applicable
Air Force | A | 0125 | A0125 | 407th Air Expeditionary Group | Expeditionary | Expeditionary | Not Applicable
Air Force | A | 0126 | A0126 | 438th Air Expeditionary Wing | Expeditionary | Expeditionary | Not Applicable
Air Force | A | 0138 | A0138 | 447th Air Expeditionary Group (Baghdad) | Expeditionary | Expeditionary | Iraq
Air Force | A | 0139 | A0139 | 455th Air Expeditionary Group | Expeditionary | Expeditionary | Not Applicable
Air Force | A | 0127 | A0127 | 506th Air Expeditionary Group | Expeditionary | Expeditionary | Not Applicable
Air Force | A | 0128 | A0128 | 64th Air Expeditionary Group | Expeditionary | Expeditionary | Not Applicable
Army | R | 0265 | R0265 | Aberdeen Proving Ground | Maryland | MD | United States
Army | R | 0266 | R0266 | Adelphi Laboratory Center | Maryland | MD | United States
Air Force | A | 0231 | A0231 | AF Financial Management Fund | Virtual | Virtual | Virtual
Air Force | A | 0228 | A0228 | Air Force 401K | Virtual | Virtual | Virtual
Air Force | A | 0226 | A0226 | Air Force Capital Improvements | Virtual | Virtual | Virtual
Air Force | A | 0225 | A0225 | Air Force Civilian Welfare | Virtual | Virtual | Virtual
Air Force | A | 0233 | A0233 | Air Force Europe - HQ | Virtual | Virtual | Virtual
Air Force | A | 0224 | A0224 | Air Force Fisher House | Virtual | Virtual | Virtual
Air Force | A | 0230 | A0230 | Air Force Insurance Fund | Virtual | Virtual | Virtual
Air Force | A | 0227 | A0227 | Air Force Lodging Fund | Virtual | Virtual | Virtual
Air Force | A | 0185 | A0185 | Air Force Materiel Command - HQ | Virtual | Virtual | Virtual
Air Force | A | 0222 | A0222 | Air Force Mission Essential Feeding Facility | Virtual | Virtual | Virtual
Air Force | A | 0223 | A0223 | Air Force Morale, Welfare, and Recreation | Virtual | Virtual | Virtual
Air Force | A | 0192 | A0192 | Air Force Reserve Command - HQ | Virtual | Virtual | Virtual
Air Force | A | 0229 | A0229 | Air Force Retirement Fund | Virtual | Virtual | Virtual
Air Force | A | 0132 | A0132 | Al Dhafra Air Base | OCONUS | United Arab Emirates | United Arab Emirates
Air Force | A | 0163 | A0163 | Altus Air Force Base | Oklahoma | OK | United States
Navy | N | 0590 | N0590 | American Forces Travel | Virtual | Virtual | Virtual
Army | R | 0267 | R0267 | Anniston Army Depot | Alabama | AL | United States
Navy | N | 0570 | N0570 | Armed Forces Retirement Home Gulfport | Mississippi | MI | United States
Navy | N | 0569 | N0569 | Armed Forces Retirement Home Washington | District of Columbia | DC | United States
Army | R | 0301 | R0301 | Army Fisher House | Virtual | Virtual | Virtual
Army | R | 0273 | R0273 | Army Recreation Machine Program, Europe District | OCONUS | Germany | Germany
Army | R | 0269 | R0269 | Army Recreation Machine Program, Far East District | OCONUS | Republic of Korea | Republic of Korea
Army | R | 0275 | R0275 | Army Ten-Miler | District of Columbia | DC | United States
Air Force | A | 0184 | A0184 | Arnold Air Force Base | Tennessee | TN | United States
Air Force | A | 0248 | A0248 | Aviano Air Base | OCONUS | Italy | Italy
Air Force | A | 0116 | A0116 | Barksdale Air Force Base | Louisiana | LA | United States
Air Force | A | 0117 | A0117 | Beale Air Force Base | California | CA | United States
Air Force | A | 0212 | A0212 | Bellows Air Force Station | Hawaii | HI | United States
Army | R | 0354 | R0354 | Bluegrass Army Depot | Kentucky | KY | United States
Air Force | A | 0174 | A0174 | Buckley Space Force Base | Colorado | CO | United States
Air Force | A | 0234 | A0234 | Buechel Air Base | OCONUS | Germany | Germany
Marines | M | 0421 | M0421 | Camp Elmore | Virginia | VA | United States
Navy | N | 0509 | N0509 | Camp Lemonnier | OCONUS | Djibouti | Djibouti
Army | R | 0278 | R0278 | Camp Mabry | Texas | TX | United States
Army | R | 0280 | R0280 | Camp Shelby Joint Forces Training Center | Mississippi | MI | United States
Army | R | 0281 | R0281 | Camp Stanley | OCONUS | Republic of Korea | Republic of Korea
Air Force | A | 0141 | A0141 | Cannon Air Force Base | New Mexico | NM | United States
Air Force | A | 0129 | A0129 | Cape Cod Air Force Station | Massachusetts | MA | United States
Army | R | 0282 | R0282 | Carlisle Barracks | Pennsylvania | PA | United States
Air Force | A | 0130 | A0130 | Cavalier Air Force Station | North Dakota | ND | United States
Air Force | A | 0131 | A0131 | Clear Air Force Station | Alaska | AK | United States
Navy | N | 0563 | N0563 | CNIC Capital Fund | Virtual | Virtual | Virtual
Navy | N | 0561 | N0561 | CNIC Child and Youth Programs | Virtual | Virtual | Virtual
Navy | N | 0565 | N0565 | CNIC Civilian Morale, Welfare and Recreation | Virtual | Virtual | Virtual
Navy | N | 0562 | N0562 | CNIC Family Readiness Warfighter & Family Support | Virtual | Virtual | Virtual
Navy | N | 0571 | N0571 | CNIC Fisher Houses | Virtual | Virtual | Virtual
Navy | N | 0587 | N0587 | CNIC IT Franchise Services | Virtual | Virtual | Virtual
Navy | N | 0560 | N0560 | CNIC Morale, Welfare and Recreation - HQ Mid-South | Virtual | Virtual | Virtual
Navy | N | 0572 | N0572 | CNIC Morale, Welfare and Recreation - HQ WNY | Virtual | Virtual | Virtual
Navy | N | 0566 | N0566 | CNIC Navy Flying Club | Virtual | Virtual | Virtual
Navy | N | 0472 | N0472 | CNIC Navy Wounded Warrior - Casualty Support | Virtual | Virtual | Virtual
Navy | N | 0473 | N0473 | CNIC Retirement Trust Agreement | Virtual | Virtual | Virtual
Navy | N | 0589 | N0589 | CNIC Treasury | Virtual | Virtual | Virtual
Army | R | 0283 | R0283 | Cold Regions Research and Engineering Laboratory (CRREL) | New Hampshire | NH | United States
Air Force | A | 0153 | A0153 | Columbus Air Force Base | Mississippi | MI | United States
Navy | N | 0546 | N0546 | Commandant Naval District Washington | Virtual | Virtual | Virtual
Navy | N | 0462 | N0462 | Commander Fleet Activities Chinhae | OCONUS | Republic of Korea | Republic of Korea
Navy | N | 0468 | N0468 | Commander Fleet Activities Okinawa | OCONUS | Japan | Japan
Navy | N | 0465 | N0465 | Commander Fleet Activities Sasebo | OCONUS | Japan | Japan
Navy | N | 0466 | N0466 | Commander Fleet Activities Yokosuka | OCONUS | Japan | Japan
Navy | N | 0541 | N0541 | Commander, Joint Region Marianas | Virtual | Virtual | Virtual
Navy | N | 0538 | N0538 | Commander, Navy Region Europe Africa Central Region | Virtual | Virtual | Virtual
Navy | N | 0539 | N0539 | Commander, Navy Region Hawaii | Virtual | Virtual | Virtual
Navy | N | 0537 | N0537 | Commander, Navy Region Japan | Virtual | Virtual | Virtual
Navy | N | 0536 | N0536 | Commander, Navy Region Korea | Virtual | Virtual | Virtual
Navy | N | 0545 | N0545 | Commander, Navy Region Mid-Atlantic | Virtual | Virtual | Virtual
Navy | N | 0542 | N0542 | Commander, Navy Region Northwest | Virtual | Virtual | Virtual
Navy | N | 0547 | N0547 | Commander, Navy Region Southeast | Virtual | Virtual | Virtual
Navy | N | 0544 | N0544 | Commander, Navy Region Southwest | Virtual | Virtual | Virtual
Navy | N | 0448 | N0448 | Construction Battalion Center Gulfport | Mississippi | MI | United States
Air Force | A | 0106 | A0106 | Creech Air Force Base | Nevada | NV | United States
Air Force | A | 0213 | A0213 | Daegu Air Base | OCONUS | Republic of Korea | Republic of Korea
Air Force | A | 0103 | A0103 | Davis-Monthan Air Force Base | Arizona | AZ | United States
Army | R | 0286 | R0286 | Defense Depot Susquehanna, Pennsylvania (DDSP) | Pennsylvania | PA | United States
Army | R | 0371 | R0371 | Defense Distribution Depot San Joaquin | California | CA | United States
Army | R | 0290 | R0290 | Defense Finance and Accounting Service (DFAS)-Indianapolis | Indiana | IN | United States
Army | R | 0292 | R0292 | Defense General Supply Center (DGSC) Richmond | Virginia | VA | United States
Army | R | 0420 | R0420 | Defense General Supply, Belvoir | Virginia | VA | United States
Army | R | 0287 | R0287 | Defense Intelligence Agency | District of Columbia | DC | United States
Army | R | 0293 | R0293 | Defense Logistics Agency (DLA) Columbus | Ohio | OH | United States
Army | R | 0295 | R0295 | Defense Logistics Services Center (DLSC) Battle Creek | Michigan | MI | United States
Army | R | 0291 | R0291 | DFAS-Texarkana | Texas | TX | United States
Army | R | 0288 | R0288 | Directorate of Emergency Services (DES) Fort Belvoir | Virginia | VA | United States
Air Force | A | 0190 | A0190 | Dobbins Air Reserve Base | Georgia | GA | United States
Army | R | 0296 | R0296 | DoD Concessions Committee | District of Columbia | DC | United States
Air Force | A | 0164 | A0164 | Dover Air Force Base | Delaware | DE | United States
Army | R | 0297 | R0297 | Dragon Hill Lodge | OCONUS | Republic of Korea | Republic of Korea
Air Force | A | 0191 | A0191 | Duke Field | Florida | FL | United States
Air Force | A | 0118 | A0118 | Dyess Air Force Base | Texas | TX | United States
Army | R | 0299 | R0299 | Edelweiss Lodge and Resort | OCONUS | Germany | Germany
Air Force | A | 0178 | A0178 | Edwards Air Force Base | California | CA | United States
Air Force | A | 0179 | A0179 | Eglin Air Force Base | Florida | FL | United States
Air Force | A | 0214 | A0214 | Eielson Air Force Base | Alaska | AK | United States
Air Force | A | 0104 | A0104 | Ellsworth Air Force Base | South Dakota | SD | United States
Air Force | A | 0119 | A0119 | F. E. Warren Air Force Base | Wyoming | WY | United States
Air Force | A | 0105 | A0105 | Fairchild Air Force Base | Washington | WA | United States
Army | R | 0303 | R0303 | Fort Belvoir | Virginia | VA | United States
Army | R | 0305 | R0305 | Fort Bliss | Texas | TX | United States
Army | R | 0309 | R0309 | Fort Carson | Colorado | CO | United States
Army | R | 0317 | R0317 | Fort Cavazos | Texas | TX | United States
Army | R | 0310 | R0310 | Fort Detrick | Maryland | MD | United States
Army | R | 0311 | R0311 | Fort Devens | Massachusetts | MA | United States
Army | R | 0313 | R0313 | Fort George G Meade | Maryland | MD | United States
Army | R | 0316 | R0316 | Fort Hamilton | New York | NY | United States
Army | R | 0321 | R0321 | Fort Jackson | South Carolina | SC | United States
Army | R | 0322 | R0322 | Fort Knox | Kentucky | KY | United States
Army | R | 0304 | R0304 | Fort Moore | Georgia | GA | United States
Army | R | 0329 | R0329 | Fort Novosel | Alabama | AL | United States
Army | R | 0331 | R0331 | Fort Stewart-Hunter Army Airfield | Georgia | GA | United States
Army | R | 0332 | R0332 | Fort Wainwright / USAG Alaska | Alaska | AK | United States
Air Force | A | 0247 | A0247 | Ghedi Air Base | OCONUS | Italy | Italy
Air Force | A | 0208 | A0208 | Goodfellow Air Force Base | Texas | TX | United States
Air Force | A | 0120 | A0120 | Grand Forks Air Force Base | North Dakota | ND | United States
Air Force | A | 0194 | A0194 | Greater Pittsburgh Air Force Base | Pennsylvania | PA | United States
Air Force | A | 0195 | A0195 | Grissom Air Force Base | New York | NY | United States
Army | R | 0333 | R0333 | Hale Koa Hotel | Hawaii | HI | United States
Air Force | A | 0180 | A0180 | Hanscom Air Force Base | Massachusetts | MA | United States
Marines | M | 0441 | M0441 | Headquarters Marine Corps | Virtual | Virtual | United States
Air Force | A | 0186 | A0186 | Hill Air Force Base | Utah | UT | United States
Air Force | A | 0142 | A0142 | Holloman Air Force Base | New Mexico | NM | United States
Air Force | A | 0196 | A0196 | Homestead Air Reserve Base | Florida | FL | United States
Army | R | 0336 | R0336 | HQ US Army (USAR) Japan | OCONUS | Japan | Japan
Army | R | 0294 | R0294 | HQ, Defense Logistics Agency | Virginia | VA | United States
Army | R | 0337 | R0337 | HQ, Europe Oversight | OCONUS | Germany | Germany
Army | R | 0262 | R0262 | HQ, IMCOM | Texas | TX | United States
Army | R | 0339 | R0339 | HQ, Surface Deployment & Distribution Center | Illinois | IL | United States
Army | R | 0340 | R0340 | HQ, US Army South (USARSO) | Texas | TX | United States
Army | R | 0341 | R0341 | Hunter Army Airfield | Georgia | GA | United States
Air Force | A | 0144 | A0144 | Hurlburt Field | Florida | FL | United States
Army | R | 0344 | R0344 | IMCOM Europe Region | OCONUS | Germany | Germany
Air Force | A | 0253 | A0253 | Incirlik Air Base | OCONUS | Turkey | Turkey
Air Force | A | 0249 | A0249 | Izmir Air Station | OCONUS | Turkey | Turkey
Air Force | A | 0145 | A0145 | Joint Base Anacostia-Bolling | District of Columbia | DC | United States
Air Force | A | 0204 | A0204 | Joint Base Andrews | Maryland | MD | United States
Air Force | A | 0256 | A0256 | Joint Base Charleston | South Carolina | SC | United States
Air Force | A | 0255 | A0255 | Joint Base Elmendorf-Richardson | Alaska | AK | United States
Air Force | A | 0261 | A0261 | Joint Base Langley-Eustis | Virginia | VA | United States
Army | R | 0261 | R0261 | Joint Base Langley-Eustis | Virginia | VA | United States
Army | R | 0348 | R0348 | Joint Base Lewis-McChord | Washington | WA | United States
Air Force | A | 0254 | A0254 | Joint Base McGuire-Dix-Lakehurst | New Jersey | NJ | United States
Army | R | 0349 | R0349 | Joint Base Myer-Henderson Hall | Virginia | VA | United States
Marines | M | 0426 | M0426 | Joint Base Myer-Henderson Hall (Henderson Hall) | Virginia | VA | United States
Navy | N | 0489 | N0489 | Joint Base Pearl Harbor-Hickam | Hawaii | HI | United States
Air Force | A | 0262 | A0262 | Joint Base San Antonio | Texas | TX | United States
Navy | N | 0464 | N0464 | Joint Expeditionary Base Little Creek-Fort Story | Virginia | VA | United States
Army | R | 0350 | R0350 | Joint Multinational Readiness Center (JMRC), Hohenfels | OCONUS | Germany | Germany
Air Force | A | 0217 | A0217 | Kadena Air Base | OCONUS | Japan | Japan
Air Force | A | 0250 | A0250 | Kalkar Air Station | OCONUS | Germany | Germany
Air Force | A | 0263 | A0263 | Kandahar Airfield | OCONUS | Afghanistan | Afghanistan
Air Force | A | 0154 | A0154 | Keesler Air Force Base | Mississippi | MI | United States
Air Force | A | 0182 | A0182 | Kirtland Air Force Base | New Mexico | NM | United States
Air Force | A | 0235 | A0235 | Kleine Brogel Air Base | OCONUS | Belgium | Belgium
Army | R | 0335 | R0335 | Korea Region Oversight | OCONUS | Republic of Korea | Republic of Korea
Air Force | A | 0218 | A0218 | Kunsan Air Base | OCONUS | Republic of Korea | Republic of Korea
Air Force | A | 0170 | A0170 | Lajes Field | OCONUS | Portugal | Portugal
Army | R | 0352 | R0352 | Landstuhl Regional Medical Center | OCONUS | Germany | Germany
Air Force | A | 0156 | A0156 | Laughlin Air Force Base | Texas | TX | United States
Army | R | 0353 | R0353 | Letterkenny Army Depot | Pennsylvania | PA | United States
Air Force | A | 0166 | A0166 | Little Rock Air Force Base | Arkansas | AR | United States
Air Force | A | 0183 | A0183 | Los Angeles Space Force Base | California | CA | United States
Air Force | A | 0146 | A0146 | Luke Air Force Base | Arizona | AZ | United States
Air Force | A | 0148 | A0148 | MacDill Air Force Base | Florida | FL | United States
Air Force | A | 0121 | A0121 | Malmstrom Air Force Base | Montana | MT | United States
Air Force | A | 0197 | A0197 | March Air Reserve Base | California | CA | United States
Marines | M | 0419 | M0419 | Marine Barracks, Washington, D.C. | District of Columbia | DC | United States
Marines | M | 0419 | M0419 | Marine Barracks, Washington, D.C. | District of Columbia | DC | United States
Marines | M | 0437 | M0437 | Marine Corps Air Ground Combat Center, Twentynine Palms | California | CA | United States
Marines | M | 0424 | M0424 | Marine Corps Air Station Cherry Point | North Carolina | NC | United States
Marines | M | 0427 | M0427 | Marine Corps Air Station Iwakuni, Japan | OCONUS | Japan | Japan
Marines | M | 0429 | M0429 | Marine Corps Air Station Miramar | California | CA | United States
Marines | M | 0438 | M0438 | Marine Corps Air Station Yuma | Arizona | AZ | United States
Marines | M | 0428 | M0428 | Marine Corps Base Camp Lejeune | North Carolina | NC | United States
Marines | M | 0431 | M0431 | Marine Corps Base Camp Pendleton | California | CA | United States
Marines | M | 0423 | M0423 | Marine Corps Base Camp Smedley D. Butler | OCONUS | Japan | Japan
Marines | M | 0425 | M0425 | Marine Corps Base Hawaii | Hawaii | HI | United States
Marines | M | 0432 | M0432 | Marine Corps Base Quantico | Virginia | VA | United States
Marines | M | 0434 | M0434 | Marine Corps Community Services (MCCS) South Carolina | South Carolina | SC | United States
Marines | M | 0420 | M0420 | Marine Corps Logistics Base Albany | Georgia | GA | United States
Marines | M | 0420 | M0420 | Marine Corps Logistics Base Albany | Georgia | GA | United States
Marines | M | 0433 | M0433 | Marine Corps Recruit Depot San Diego | California | CA | United States
Marines | M | 0440 | M0440 | Marine Corps Recruiting Command Garden City | New York | NY | United States
Air Force | A | 0206 | A0206 | Maxwell Air Force Base | Alabama | AL | United States
Army | R | 0355 | R0355 | McAlester Army Ammunition Plant | Oklahoma | OK | United States
Air Force | A | 0111 | A0111 | McConnell Air Force Base | Kansas | KS | United States
Navy | N | 0588 | N0588 | Military Ticket Program | Virtual | Virtual | Virtual
Air Force | A | 0198 | A0198 | Minneapolis-St Paul Air Reserve Station | Minnesota | MN | United States
Air Force | A | 0110 | A0110 | Minot Air Force Base | North Dakota | ND | United States
Air Force | A | 0215 | A0215 | Misawa Air Base | OCONUS | Japan | Japan
Air Force | A | 0157 | A0157 | Moody Air Force Base | Georgia | GA | United States
Air Force | A | 0246 | A0246 | Moron Air Base | OCONUS | Spain | Spain
Air Force | A | 0147 | A0147 | Mountain Home Air Force Base | Idaho | ID | United States
Army | R | 0357 | R0357 | National Geospatial-Intelligence Agency (NGA) East | Maryland | MD | United States
Army | R | 0358 | R0358 | National Geospatial-Intelligence Agency (NGA) West | Missouri | MO | United States
Army | R | 0359 | R0359 | National Ground Intelligence | Virginia | VA | United States
Army | R | 0419 | R0419 | National Security Agency | Maryland | MD | United States
Air Force | A | 0239 | A0239 | NATO Air Base Geilenkirchen | OCONUS | Germany | Germany
Army | R | 0360 | R0360 | NATO School - Oberammergau | OCONUS | Germany | Germany
Navy | N | 0503 | N0503 | Naval Air Facility El Centro | California | CA | United States
Navy | N | 0478 | N0478 | Naval Air Station Corpus Christi | Texas | TX | United States
Navy | N | 0497 | N0497 | Naval Air Station Fallon | Nevada | NV | United States
Navy | N | 0449 | N0449 | Naval Air Station Jacksonville | Florida | FL | United States
Navy | N | 0474 | N0474 | Naval Air Station Joint Reserve Base Fort Worth | Texas | TX | United States
Navy | N | 0480 | N0480 | Naval Air Station Joint Reserve Base New Orleans | Louisiana | LA | United States
Navy | N | 0446 | N0446 | Naval Air Station Key West | Florida | FL | United States
Navy | N | 0479 | N0479 | Naval Air Station Kingsville | Texas | TX | United States
Navy | N | 0506 | N0506 | Naval Air Station Lemoore | California | CA | United States
Navy | N | 0475 | N0475 | Naval Air Station Meridian | Mississippi | MI | United States
Navy | N | 0451 | N0451 | Naval Air Station Oceana | Virginia | VA | United States
Navy | N | 0482 | N0482 | Naval Air Station Patuxent River | Maryland | MD | United States
Navy | N | 0476 | N0476 | Naval Air Station Pensacola | Florida | FL | United States
Navy | N | 0493 | N0493 | Naval Air Station Whidbey Island | Washington | WA | United States
Navy | N | 0477 | N0477 | Naval Air Station Whiting Field Milton | Florida | FL | United States
Navy | N | 0504 | N0504 | Naval Air Weapons Station China Lake | California | CA | United States
Navy | N | 0498 | N0498 | Naval Base Coronado | California | CA | United States
Navy | N | 0501 | N0501 | Naval Base Guam | Guam | Guam | United States
Navy | N | 0492 | N0492 | Naval Base Kitsap | Washington | WA | United States
Navy | N | 0514 | N0514 | Naval Base Point Loma | California | CA | United States
Navy | N | 0540 | N0540 | Naval Base San Diego | California | CA | United States
Navy | N | 0500 | N0500 | Naval Base Ventura County | California | CA | United States
Navy | N | 0452 | N0452 | Naval Magazine Indian Island | Washington | WA | United States
Navy | N | 0513 | N0513 | Naval Ordnance Test Unit Cape Canaveral | Florida | FL | United States
Navy | N | 0494 | N0494 | Naval Station Everett | Washington | WA | United States
Navy | N | 0444 | N0444 | Naval Station Great Lakes | Illinois | IL | United States
Navy | N | 0445 | N0445 | Naval Station Mayport | Florida | FL | United States
Navy | N | 0460 | N0460 | Naval Station Newport | Rhode Island | RI | United States
Navy | N | 0455 | N0455 | Naval Station Norfolk | Virginia | VA | United States
Navy | N | 0516 | N0516 | Naval Submarine Base Kings Bay | Georgia | GA | United States
Navy | N | 0463 | N0463 | Naval Submarine Base New London | Connecticut | CT | United States
Navy | N | 0502 | N0502 | Naval Support Activity Andersen | Guam | Guam | United States
Navy | N | 0485 | N0485 | Naval Support Activity Annapolis | Maryland | MD | United States
Navy | N | 0484 | N0484 | Naval Support Activity Bethesda | Maryland | MD | United States
Navy | N | 0443 | N0443 | NAVWPNSTA Crane | Indiana | IN | United States
Navy | N | 0456 | N0456 | Naval Support Activity Hampton Roads | Virginia | VA | United States
Navy | N | 0457 | N0457 | Naval Support Activity Mechanicsburg | Pennsylvania | PA | United States
Navy | N | 0505 | N0505 | Naval Support Activity Mechanicsburg Det | Pennsylvania | PA | United States
Navy | N | 0481 | N0481 | Naval Support Activity Mid-South | Tennessee | TN | United States
Navy | N | 0496 | N0496 | Naval Support Activity Monterey | California | CA | United States
Navy | N | 0510 | N0510 | Naval Support Activity Orlando | Florida | FL | United States
Navy | N | 0447 | N0447 | Naval Support Activity Panama City | Florida | FL | United States
Navy | N | 0458 | N0458 | Naval Support Activity Saratoga Springs | New York | NY | United States
Navy | N | 0487 | N0487 | Naval Support Activity South Potomac Dahlgren | Virginia | VA | United States
Navy | N | 0520 | N0520 | Naval Support Activity Wallops Island | Virginia | VA | United States
Navy | N | 0483 | N0483 | Naval Support Facility Indian Head | Maryland | MD | United States
Navy | N | 0459 | N0459 | Naval Weapons Station Earle Colts Neck | New Jersey | NJ | United States
Navy | N | 0515 | N0515 | Naval Weapons Station Seal Beach | California | CA | United States
Navy | N | 0450 | N0450 | Naval Weapons Station Yorktown | Virginia | VA | United States
Navy | N | 0495 | N0495 | Navy Recreation Area Jim Creek | Washington | WA | United States
Navy | N | 0491 | N0491 | Navy Recreation Area Pacific Beach | Washington | WA | United States
Navy | N | 0507 | N0507 | Navy Recreation Area Solomons | Maryland | MD | United States
Air Force | A | 0149 | A0149 | Nellis Air Force Base | Nevada | NV | United States
Air Force | A | 0199 | A0199 | Niagara Falls Air Reserve Station | New York | NY | United States
Navy | N | 0453 | N0453 | Norfolk Naval Shipyard | Virginia | VA | United States
Army | R | 0361 | R0361 | Office of Chief of Chaplains (OCCH) | District of Columbia | DC | United States
Air Force | A | 0112 | A0112 | Offutt Air Force Base | Nebraska | NE | United States
Air Force | A | 0220 | A0220 | Osan Air Base | OCONUS | Republic of Korea | Republic of Korea
Navy | N | 0568 | N0568 | OSD CNIC Millington | Virtual | Virtual | Virtual
Navy | N | 0490 | N0490 | Pacific Missile Range Facility Barking Sands | Hawaii | HI | United States
Air Force | A | 0181 | A0181 | Patrick Space Force Base | Florida | FL | United States
Air Force | A | 0205 | A0205 | Pentagon | Virginia | VA | United States
Army | R | 0365 | R0365 | Pentagon Athletic Center (PAC) | District of Columbia | DC | United States
Air Force | A | 0173 | A0173 | Peterson Space Force Base | Colorado | CO | United States
Air Force | A | 0200 | A0200 | Portland International Airport Air Guard Station | Oregon | OR | United States
Navy | N | 0461 | N0461 | Portsmouth Naval Shipyard | New Hampshire | NH | United States
Air Force | A | 0123 | A0123 | Prince Sultan Air Base | Expeditionary | Expeditionary | Saudi Arabia
Army | R | 0421 | R0421 | Pueblo Army Depot | Colorado | CO | United States
Air Force | A | 0237 | A0237 | Ramstein Air Base | OCONUS | Germany | Germany
Army | R | 0366 | R0366 | Red River Army Depot | Texas | TX | United States
Army | R | 0367 | R0367 | Redstone Arsenal | Alabama | AL | United States
Air Force | A | 0155 | A0155 | Reserved | Not Applicable | Not Applicable | Not Applicable
Air Force | A | 0158 | A0158 | Reserved | Not Applicable | Not Applicable | Not Applicable
Air Force | A | 0165 | A0165 | Reserved | Not Applicable | Not Applicable | Not Applicable
Air Force | A | 0167 | A0167 | Reserved | Not Applicable | Not Applicable | Not Applicable
Air Force | A | 0177 | A0177 | Reserved | Not Applicable | Not Applicable | Not Applicable
Air Force | A | 0209 | A0209 | Reserved | Not Applicable | Not Applicable | Not Applicable
Air Force | A | 0187 | A0187 | Robins Air Force Base | Georgia | GA | United States
Army | R | 0369 | R0369 | Rock Island Corps of Engineers (COE) | Illinois | IL | United States
Air Force | A | 0244 | A0244 | Royal Air Force Alconbury, Royal Air Force Molesworth, Royal Air Force Upwood | OCONUS | United Kingdom | United Kingdom
Air Force | A | 0243 | A0243 | Royal Air Force Croughton | OCONUS | United Kingdom | United Kingdom
Air Force | A | 0245 | A0245 | Royal Air Force Fairford | OCONUS | United Kingdom | United Kingdom
Air Force | A | 0241 | A0241 | Royal Air Force Lakenheath | OCONUS | United Kingdom | United Kingdom
Air Force | A | 0240 | A0240 | Royal Air Force Menwith Hill | OCONUS | United Kingdom | United Kingdom
Air Force | A | 0242 | A0242 | Royal Air Force Mildenhall | OCONUS | United Kingdom | United Kingdom
Air Force | A | 0172 | A0172 | Schriever Space Force Base | Colorado | CO | United States
Air Force | A | 0169 | A0169 | Scott Air Force Base | Illinois | IL | United States
Air Force | A | 0150 | A0150 | Seymour Johnson Air Force Base | North Carolina | NC | United States
Army | R | 0372 | R0372 | Shades of Green | Florida | FL | United States
Army | R | 0373 | R0373 | Sharpe Army Depot | California | CA | United States
Air Force | A | 0151 | A0151 | Shaw Air Force Base | South Carolina | SC | United States
Air Force | A | 0159 | A0159 | Sheppard Air Force Base | Texas | TX | United States
Army | R | 0374 | R0374 | Sierra Army Depot | California | CA | United States
Navy | N | 0521 | N0521 | NSA Singapore | OCONUS | Singapore | Singapore
Army | R | 0375 | R0375 | Soto Cano Air Base | OCONUS | Honduras | Honduras
Air Force | A | 0238 | A0238 | Spangdahlem Air Base | OCONUS | Germany | Germany
Army | R | 0378 | R0378 | Stars & Stripes Pacific | OCONUS | Japan | Japan
Army | R | 0376 | R0376 | Stars & Stripes, HQ | District of Columbia | DC | United States
Air Force | A | 0252 | A0252 | Stavanger Air Base | OCONUS | Norway | Norway
Army | R | 0380 | R0380 | The Judge Advocate General's Legal Center and School | Virginia | VA | United States
Army | R | 0320 | R0320 | The National Training Center and Fort Irwin | California | CA | United States
Air Force | A | 0176 | A0176 | Thule Air Base | OCONUS | Greenland | Greenland
Air Force | A | 0188 | A0188 | Tinker Air Force Base | Oklahoma | OK | United States
Army | R | 0381 | R0381 | Tobyhanna Army Depot | Pennsylvania | PA | United States
Army | R | 0382 | R0382 | Tooele Army Depot | Utah | UT | United States
Air Force | A | 0152 | A0152 | Travis Air Force Base | California | CA | United States
Army | R | 0383 | R0383 | Tripler Army Medical Center | Hawaii | HI | United States
Air Force | A | 0175 | A0175 | Tyndall Air Force Base | Florida | FL | United States
Air Force | A | 0207 | A0207 | U.S. Air Force Academy | Colorado | CO | United States
Army | R | 0362 | R0362 | U.S. Army - Parks Reserve Forces Training Area (Camp Parks) | California | CA | United States
Army | R | 0412 | R0412 | U.S. Army Chaplain Center and School | South Carolina | SC | United States
Army | R | 0289 | R0289 | U.S. Army Detroit Arsenal | Michigan | MI | United States
Army | R | 0298 | R0298 | U.S. Army Dugway Proving Ground | Utah | UT | United States
Army | R | 0307 | R0307 | U.S. Army Fort Buchanan Puerto Rico | Puerto Rico | PR | United States
Army | R | 0308 | R0308 | U.S. Army Fort Campbell | Kentucky | KY | United States
Army | R | 0312 | R0312 | U.S. Army Fort Drum | New York | NY | United States
Army | R | 0314 | R0314 | U.S. Army Fort Eisenhower | Georgia | GA | United States
Army | R | 0324 | R0324 | U.S. Army Fort Gregg-Adams | Virginia | VA | United States
Army | R | 0318 | R0318 | U.S. Army Fort Huachuca | Arizona | AZ | United States
Army | R | 0323 | R0323 | U.S. Army Fort Leavenworth | Kansas | KS | United States
Army | R | 0325 | R0325 | U.S. Army Fort Leonard Wood | Missouri | MO | United States
Army | R | 0306 | R0306 | U.S. Army Fort Liberty | North Carolina | NC | United States
Army | R | 0326 | R0326 | U.S. Army Fort McCoy | Wisconsin | WI | United States
Army | R | 0328 | R0328 | U.S. Army Fort Riley | Kansas | KS | United States
Army | R | 0386 | R0386 | U.S. Army Garrison Ansbach | OCONUS | Germany | Germany
Army | R | 0388 | R0388 | U.S. Army Garrison Baumholder | OCONUS | Germany | Germany
Army | R | 0389 | R0389 | U.S. Army Garrison Bavaria | OCONUS | Germany | Germany
Army | R | 0390 | R0390 | U.S. Army Garrison Benelux | OCONUS | Belgium | Belgium
Army | R | 0391 | R0391 | U.S. Army Garrison Brussels | OCONUS | Belgium | Belgium
Army | R | 0279 | R0279 | U.S. Army Garrison Camp Red Cloud | OCONUS | Republic of Korea | Republic of Korea
Army | R | 0276 | R0276 | U.S. Army Garrison Casey | OCONUS | Republic of Korea | Republic of Korea
Army | R | 0392 | R0392 | U.S. Army Garrison Daegu | OCONUS | Republic of Korea | Republic of Korea
Army | R | 0315 | R0315 | U.S. Army Garrison Fort Greely | Alaska | AK | United States
Army | R | 0319 | R0319 | U.S. Army Garrison Fort Hunter Liggett | California | CA | United States
Army | R | 0330 | R0330 | U.S. Army Garrison Fort Sill | Oklahoma | OK | United States
Army | R | 0393 | R0393 | U.S. Army Garrison Garmisch | OCONUS | Germany | Germany
Army | R | 0394 | R0394 | U.S. Army Garrison Hawaii | Hawaii | HI | United States
Army | R | 0395 | R0395 | U.S. Army Garrison Hohenfels | OCONUS | Germany | Germany
Army | R | 0277 | R0277 | U.S. Army Garrison Humphreys | OCONUS | Republic of Korea | Republic of Korea
Army | R | 0406 | R0406 | U.S. Army Garrison Italy | OCONUS | Italy | Italy
Army | R | 0396 | R0396 | U.S. Army Garrison Japan | OCONUS | Japan | Japan
Army | R | 0409 | R0409 | U.S. Army Garrison Kwajalein-Atoll | OCONUS | Republic of the Marshall Islands | Republic of the Marshall Islands
Army | R | 0397 | R0397 | U.S. Army Garrison Livorno | OCONUS | Italy | Italy
Army | R | 0398 | R0398 | U.S. Army Garrison Miami | Florida | FL | United States
Army | R | 0399 | R0399 | U.S. Army Garrison Okinawa | OCONUS | Japan | Japan
Army | R | 0363 | R0363 | U.S. Army Garrison Picatinny Arsenal | New Jersey | NJ | United States
Army | R | 0364 | R0364 | U.S. Army Garrison Pine Bluff Arsenal | Arkansas | AR | United States
Army | R | 0400 | R0400 | U.S. Army Garrison Pohakuloa Training Area | Hawaii | HI | United States
Army | R | 0401 | R0401 | U.S. Army Garrison Presidio Of Monterey | California | CA | United States
Army | R | 0402 | R0402 | U.S. Army Garrison Rheinland-Pfalz | OCONUS | Germany | Germany
Army | R | 0368 | R0368 | U.S. Army Garrison Rock Island Arsenal | Illinois | IL | United States
Army | R | 0403 | R0403 | U.S. Army Garrison Schinnen | OCONUS | Netherlands | Netherlands
Army | R | 0405 | R0405 | U.S. Army Garrison Stuttgart | OCONUS | Germany | Germany
Army | R | 0407 | R0407 | U.S. Army Garrison Wiesbaden | OCONUS | Germany | Germany
Army | R | 0408 | R0408 | U.S. Army Garrison Yongsan | OCONUS | Republic of Korea | Republic of Korea
Army | R | 0418 | R0418 | U.S. Army Garrison Yuma Proving Ground | Arizona | AZ | United States
Army | R | 0327 | R0327 | U.S. Army JRTC and Fort Johnson | Louisiana | LA | United States
Army | R | 0356 | R0356 | U.S. Army Natick Soldier Systems Center | Massachusetts | MA | United States
Army | R | 0410 | R0410 | U.S. Army Publications Distribution Center | Missouri | MO | United States
Army | R | 0411 | R0411 | U.S. Military Academy at West Point | New York | NY | United States
Navy | N | 0529 | N0529 | U.S. National Support Element Latina | OCONUS | Italy | Italy
Navy | N | 0526 | N0526 | U.S. National Support Element Lisbon | OCONUS | Portugal | Portugal
Navy | N | 0527 | N0527 | U.S. National Support Element Madrid | OCONUS | Spain | Spain
Navy | N | 0528 | N0528 | U.S. National Support Element Valencia | OCONUS | Spain | Spain
Navy | N | 0533 | N0533 | U.S. National Support Element, Fujurah | OCONUS | United Arab Emirates | United Arab Emirates
Navy | N | 0531 | N0531 | U.S. National Support Element, Isa | OCONUS | Bahrain | Bahrain
Navy | N | 0532 | N0532 | U.S. National Support Element, Jebel Ali | OCONUS | Bahrain | Bahrain
Navy | N | 0573 | N0573 | U.S. Naval Academy Business Services Division | Virtual | Virtual | Virtual
Navy | N | 0575 | N0575 | U.S. Naval Academy Candidate Guidance Fund | Virtual | Virtual | Virtual
Navy | N | 0499 | N0499 | U.S. Naval Academy Midshipmen Rations | Virtual | Virtual | Virtual
Navy | N | 0574 | N0574 | U.S. Naval Academy Midshipmen Welfare Fund | Virtual | Virtual | Virtual
Navy | N | 0467 | N0467 | U.S. Naval Air Facility Atsugi | OCONUS | Japan | Japan
Navy | N | 0470 | N0470 | U.S. Naval Air Station Sigonella | OCONUS | Italy | Italy
Navy | N | 0523 | N0523 | U.S. Naval Joint Services Activity The New Sanno | OCONUS | Japan | Japan
Navy | N | 0442 | N0442 | U.S. Naval Station Guantanamo Bay | OCONUS | Cuba | Cuba
Navy | N | 0469 | N0469 | U.S. Naval Station Rota | OCONUS | Spain | Spain
Navy | N | 0508 | N0508 | U.S. Naval Support Activity Bahrain | OCONUS | Bahrain | Bahrain
Navy | N | 0471 | N0471 | U.S. Naval Support Activity Naples | OCONUS | Italy | Italy
Navy | N | 0522 | N0522 | U.S. Naval Support Activity Naples Det Gaeta | OCONUS | Italy | Italy
Navy | N | 0518 | N0518 | U.S. Naval Support Activity Souda Bay | OCONUS | Greece | Greece
Navy | N | 0535 | N0535 | U.S. Naval Support Facility Deveselu | OCONUS | Romania | Romania
Navy | N | 0511 | N0511 | U.S. Naval Support Facility Diego Garcia | OCONUS | United Kingdom | United Kingdom
Navy | N | 0512 | N0512 | U.S. Naval Support Facility Redzikowo | OCONUS | Poland | Poland
Army | R | 0384 | R0384 | Umatilla Chemical Depot | Oregon | OR | United States
Army | R | 0385 | R0385 | Uniformed Services University of Health Science (USUHS) | Maryland | MD | United States
Air Force | A | 0135 | A0135 | United States Military Training Mission, Riyadh | OCONUS | Saudi Arabia | Saudi Arabia
Army | R | 0302 | R0302 | US Army Fort Walker | Virginia | VA | United States
Navy | N | 0555 | N0555 | USS Abraham Lincoln (CVN 72) | Ship | Ship | United States
Navy | N | 0552 | N0552 | USS Carl Vinson (CVN 70) | Ship | Ship | United States
Navy | N | 0548 | N0548 | USS Dwight D. Eisenhower (CVN 69) | Ship | Ship | United States
Navy | N | 0558 | N0558 | USS George H. W. Bush (CVN 77) | Ship | Ship | United States
Navy | N | 0551 | N0551 | USS George Washington (CVN 73) | Ship | Ship | United States
Navy | N | 0559 | N0559 | USS Gerald R. Ford (CVN 78) | Ship | Ship | United States
Navy | N | 0556 | N0556 | USS Harry S Truman (CVN 75) | Ship | Ship | United States
Navy | N | 0550 | N0550 | USS John C Stennis (CVN 74) | Ship | Ship | United States
Navy | N | 0553 | N0553 | USS Nimitz (CVN 68) | Ship | Ship | United States
Navy | N | 0557 | N0557 | USS Ronald Reagan (CVN 76) | Ship | Ship | United States
Navy | N | 0549 | N0549 | USS Theodore Roosevelt (CVN 71) | Ship | Ship | United States
Air Force | A | 0160 | A0160 | Vance Air Force Base | Oklahoma | OK | United States
Air Force | A | 0115 | A0115 | Vandenberg Space Force Base | California | CA | United States
Air Force | A | 0236 | A0236 | Vogelweh/Sembach | OCONUS | Germany | Germany
Air Force | A | 0221 | A0221 | Volkel Air Base | OCONUS | Germany | Germany
Navy | N | 0488 | N0488 | Washington Navy Yard | District of Columbia | DC | United States
Army | R | 0414 | R0414 | Watervliet Arsenal | New York | NY | United States
Air Force | A | 0201 | A0201 | Westover Air Reserve Base | Massachusetts | MA | United States
Army | R | 0415 | R0415 | White Sands Missile Range | New Mexico | NM | United States
Air Force | A | 0122 | A0122 | Whiteman Air Force Base | Missouri | MO | United States
Army | R | 0416 | R0416 | William Beaumont Army Medical Center | Texas | TX | United States
Air Force | A | 0189 | A0189 | Wright-Patterson Air Force Base | Ohio | OH | United States
Army | R | 0417 | R0417 | Yakima Training Center | Washington | WA | United States
Air Force | A | 0216 | A0216 | Yokota Air Base | OCONUS | Japan | Japan
Air Force | A | 0202 | A0202 | Youngstown Air Reserve Station | Ohio | OH | United States

## (1) Major Const Proj Sum Data
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
PY2027 Major Construction Program Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0). The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
(5) | Input contracting method used as defined in Enclosure 2 of DoWI 7700.18 of December 15, 2004: Design/Build (E2.1.18), Turnkey (E.2.1.30) or traditional Design-Bid-Build.
Information Provider | Component | Installation (1) | Installation Code (2) | State / Country | Project Title | Project Number (3) | DoW 4-digit FAC Code (4) | Scope | Scope Type | Construction Cost ($000) | Total Investment Cost ($000) | Design Stage (%) | NPV ($000) | IRR (%) | Payback Period (Years) | Contract Award Date (MM/DD/YYYY) | Expected Completion Date (MM/DD/YYYY) | Funding | Program | Design/Build, Turnkey, or Design/Bid/Build (5) | Cat (A,B,C) | Design Cost | Equipment Cost
Policy Requiring Waiver:
1 | In accordance with DoW Instruction 1015.15, Lodging Program Resource Management, Temporary Duty (TDY) lodging facilities are to be constructed with appropriated
funds unless the Secretary of the Military Department or the Military Service headquarters designee concerned has certified that APF is unavailable recognizing
that the waiver of fund source will create higher NAF expenses and possibly higher lodging service charges.
2 | In accordance with DOW Instruction 1015.15, Procedures for Establishment, Management, and Control of Nonappropriated Fund Instrumentalities and Financial
Management of Supporting Resources, appropriated funds are to be used for youth centers, courts, and playing fields outside the continental U.S. unless the
Secretary of the Military Department concerned has certified that APF is unavailable.
3 | In accordance with DOW Instruction 1330.21, Armed Services Exchange Regulations (ASER), when establishing name-brand fast-food (NBFF) operations, concession
operations are preferred in the United States. Notice of deviations from the preferred method that results in major construction projects shall accompany the
major construction program and shall include the evaluation of economic and non-economic factors.
4 | In accordance with DOW Instruction 7700.18, Commissary Surcharge, Nonappropriated Fund (NAF), and Privately Financed Construction Report Procedures, project
design shall be 35 percent complete when submitted to USD(P&R) except design/build or turnkey contracts, which must be at least 15 percent complete.
5 | In accordance with the PDUSD(P&R) December 4, 2007 memorandum, the Military Department may request a deviation or exception to use nonappropriated funds in lieu
of appropriations when all of the following criteria are satisfied: (1) the Military Department included the project in its Military Construction (MILCON)
(major and minor construction) or APF modernization budget submission to the USD(C); (2) the project was not included in the President's Budget submission to
the Congress or was not approved by the Congress; (3) failure to build the facility will seriously impact quality of life of military personnel and their
families; (4) the Military Service certifies that the project is of higher priority than all other non-funded NAF construction (major and minor) and
modernization requirements; and (5) the Military Department endorses the use of NAF.

## (2) Major Proj Req Waivers
ENCLOSURE 4
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
PY2027 Major Projects Requiring Waivers
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation Code corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
(5) | Please specify the policy requiring waiver in the table below.
Information Provider | Component | Installation (1) | Installation Code (2) | State / Country | Project Title | Project Number (3) | DoW 4-digit FAC Code (4) | Project / Cost Avoidance ($000) | Note (5)
Policy Requiring Waiver:
1 | In accordance with DoW Instruction 1015.15, Lodging Program Resource Management, Temporary Duty (TDY) lodging facilities are to be constructed with appropriated
funds unless the Secretary of the Military Department or the Military Service headquarters designee concerned has certified that APF is unavailable recognizing
that the waiver of fund source will create higher NAF expenses and possibly higher lodging service charges.
2 | In accordance with DOW Instruction 1015.15, Procedures for Establishment, Management, and Control of Nonappropriated Fund Instrumentalities and Financial
Management of Supporting Resources, appropriated funds are to be used for youth centers, courts, and playing fields outside the continental U.S. unless the
Secretary of the Military Department concerned has certified that APF is unavailable.
3 | In accordance with DOW Instruction 1330.21, Armed Services Exchange Regulations (ASER), when establishing name-brand fast-food (NBFF) operations, concession
operations are preferred in the United States. Notice of deviations from the preferred method that results in major construction projects shall accompany the
major construction program and shall include the evaluation of economic and non-economic factors.
4 | In accordance with DOW Instruction 7700.18, Commissary Surcharge, Nonappropriated Fund (NAF), and Privately Financed Construction Report Procedures, project
design shall be 35 percent complete when submitted to USD(P&R) except design/build or turnkey contracts, which must be at least 15 percent complete.
5 | In accordance with the PDUSD(P&R) December 4, 2007 memorandum, the Military Department may request a deviation or exception to use nonappropriated funds in lieu
of appropriations when all of the following criteria are satisfied: (1) the Military Department included the project in its Military Construction (MILCON)
(major and minor construction) or APF modernization budget submission to the USD(C); (2) the project was not included in the President's Budget submission to
the Congress or was not approved by the Congress; (3) failure to build the facility will seriously impact quality of life of military personnel and their
families; (4) the Military Service certifies that the project is of higher priority than all other non-funded NAF construction (major and minor) and
modernization requirements; and (5) the Military Department endorses the use of NAF.

## (3) Minor Const Proj Sum Data
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
PY2027 Minor Construction Program Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0). The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
Information Provider | Component | Installation (1) | Installation Code (2) | State / Country | Project Title | Project Number (3) | DoW 4-digit FAC Code (4) | Construction Cost ($000) | Total Investment Cost ($000) | Scope | Scope Type | Contract Award Date (MM/DD/YYYY) | Funding | Design Cost | Equipment Cost

## (4) Cancelled Const Proj Sum
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
PY2027 Cancelled Major Construction Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
Information Provider | Component | FY Approved | Installation (1) | Installation Code (2) | State / Country | Project Title | Project Number (3) | DoW 4-digit FAC Code (4) | Total Investment Cost ($000) | Rationale for Cancellation
*** A summary paragraph shall be provided describing the rationale for each canceled project. ****

## (5) Delayed Contract Award Sum
ENCLOSURE 3
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed Construction
PY2027 Delayed Contract Award Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
Information Provider | Component | FY Approved | Installation (1) | Installation Code (2) | State / Country | Project Title | Project Number (3) | DoW 4-digit FAC Code (4) | Construction Cost ($000) | Total Investment Cost ($000) | Estimated Contract Award Date (MM-DD-YYYY) | Rationale for Delay
*** A summary paragraph shall be provided describing the rationale for each delayed project. ****

## (6) Cost and Scope Change
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
PY2027 Notification of Prior Years Construction Cost Increase or Deviation in Scope Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0). The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
Information Provider | Component | FY Approved | Installation (1) | Installation Code (2) | State / Country | Project Title | Project Number (3) | DoW 4-digit FAC Code (4) | Approved Construction Cost ($000) | Approved Cost Scope | Approved Cost Scope Type | New Construction Cost ($000) | New Construction Scope | New Construction Scope Type | Rationale for Cost / Scope Change
*** A summary paragraph shall be provided describing the rationale for each cost/scope change project. ****

## (7) MILCON
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed Construction
PY2027 Military Construction (MILCON) Appropriation Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell.
Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
Information Provider | Component | Installation (1) | Installation Code (2) | State / Country | Project Title | Project Number (3) | DoW 4-digit FAC Code (4) | Total Investment Cost ($000)

## (8) Public-Private Ventures
ENCLOSURE 5
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
PY2027 Proposed Public Private Venture Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation Code corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
Information Provider | Component | Original Program Year | Installation (1) | Installation Code (2) | State / Country | Project Number (3) | Project Title | DoW 4-digit FAC Code (4) | Proposed Cost Avoidance ($000)
Information Provider | Component | Original Program Year | Installation (1) | Installation Code (2) | State / Country | Project Number (3) | Project Title | DoW 4-digit FAC Code (4) | Proposed Cost Avoidance ($000)

## (9) Enhanced Use Lease Summary
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
PY2027 Enhanced Use Lease Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
Information Provider | Component | Program Year | Installation | Installation Code | State / Country | Leasing Entity | Total Value ($000)

## (10) Status of Major Projects
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed Construction
PY2027 Status of Previously Approved Major Construction Projects
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0). The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoW Facility Analysis Category Code. Please make sure to use the 4 digit code.
(5) | Only report actual dates. Otherwise, please leave blank.
(6) | Once projects have completed their post validation assessment and have been briefed to OSW they no longer need to be reported on this form.
Information Provider | Component | FY Approved | Installation | Installation Code (2) | State / Country | Project Title | Project Number (3) | DoW 4-digit FAC Code (4) | Initial Approved Total Investment ($000) | Current Approved Total Investment ($000) | Initial Approved Project Scope | Initial Approved Project Scope Type | Current Approved Project Scope | Current Approved Project Scope Type | Contract Award Date (MM/DD/YYYY) (5) | Total Investment Cost to Date ($000) | Estimated Outstanding Total Investment Cost ($000) | Actual Completion Date (MM/DD/YYYY) (5) | Funding | Projected Total Investment Cost | Actual Date Post Occupancy Review Completed (MM/DD/YYYY) (5, 6) | Post Occupancy Review (POR) Explanation | Notes
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## (11) PY2027 Capital Investment
Department of War
Commissary Surcharge, Nonappropriated Fund, and Privately Financed Construction
PY2027 Annual Capital Investment Programs Summary Data (As of May 15, 2026)
($000s)
Note: - Please populate cells that are shaded light blue. - Update cells shaded light purple as needed
Service Programs |  | Year -3 (2023) | Year -2 (2024) | Year -1 (2025) | Current Year (2026) | Program Year (2027) | Program Year +1 (2028)
Army Lodging
| Facilities and Improvements (Land and Structures) | 42700 | 25000 | 30600 | 64000 | 72300 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furniture, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | 42700 | 25000 | 30600 | 64000 | 72300 | 0
Army Civilian MWR
| Facilities and Improvements (Land and Structures) | -109 | 0 | 0 | 0 | 0 | 0
| Major and Minor Construction | -130 | 159 | 47 | 48 | 49 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furniture, Fixtures and Equipment | -2198 | -142 | -144 | -149 | -153 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | -2307 | -142 | -144 | -149 | -153 | 0
Army Military MWR
| Facilities and Improvements (Land and Structures) | -747 | 11109 | 5459 | 5623 | 5791 | 0
| Major and Minor Construction | 9384 | 91589 | 10005 | 42235 | 43502 | 0
| All Other Facility Investment | -1080 | 1236 | -575 | -593 | -610 | 0
| Furniture, Fixtures and Equipment | -2620 | 13391 | 6934 | 7142 | 7357 | 0
| Information Technology | 2959 | 4384 | 2959 | 3048 | 3139 | 0
| Sub Total | -408 | 28884 | 15352 | 15813 | 16287 | 0
Army Supplemental Mission
| Facilities and Improvements (Land and Structures) | -275 | 335 | 198 | 204 | 210 | 0
| Major and Minor Construction | -3476 | -456 | -156 | -160 | -165 | 0
| All Other Facility Investment | -6 | -1 | -6 | -6 | -6 | 0
| Furniture, Fixtures and Equipment | -7987 | -1161 | -399 | -411 | -423 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | -8262 | -826 | -201 | -207 | -213 | 0
NAVY Exchange
| Facilities and Improvements (Land and Structures) | 8731 | 10796 | 7500 | 23600 | 91200 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 21466 | 20335 | 31400 | 30000 | 36400 | 0
| Information Technology | 4897 | 15208 | 28557 | 28339 | 25541 | 0
| Sub Total | 35094 | 46339 | 67457 | 81939 | 153141 | 0
NAVY Military MWR
| Facilities and Improvements (Land and Structures) | 10000 | 14020 | 45270 | 52200 | 65000 | 0
| Major and Minor Construction | 9963 | 9346 | 30180 | 34800 | 15000 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 6622 | 13030 | 15000 | 15000 | 10000 | 0
| Information Technology | 5812 | 4660 | 5948 | 6097 | 6100 | 0
| Sub Total | 22434 | 31710 | 66218 | 73297 | 81100 | 0
NAVY Civilian MWR
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 0 | 0 | 115 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 115 | 0 | 0 | 0
NAVY (NEXCOM) Hospitality group (NHG) Lodging - Navy Lodge and NGIS merged into one NAFI NHG
| Facilities and Improvements (Land and Structures) | 114900 | 213800 | 175000 | 413900 | 297400 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 5900 | 42223 | 95000 | 65000 | 58000 | 0
| Information Technology | 0 | 0 | 5000 | 3000 | 3000 | 0
| Sub Total | 120800 | 256023 | 275000 | 481900 | 358400 | 0
NAVY Supplemental Mission
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
MCCS Exchange
| Facilities and Improvements (Land and Structures) | 7611 | 14587.5568 | 28495.7457 | 18289.5259 | 3812.967 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 3404 | 4346.573 | 2777.2894 | 2806.4369 | 1636.6754 | 0
| Information Technology | 1258 | 11681.4778 | 11166.7232 | 10034.2611 | 2080.9498 | 0
| Sub Total | 12273 | 30615.6076 | 42439.7583 | 31130.2239 | 7530.5922 | 0
MCCS Military MWR
| Facilities and Improvements (Land and Structures) | 13575.96 | 8219.2744 | 39974.7142 | 38433.4267 | 15655.8021 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 3430.7 | 4557.549 | 9980.8176 | 9309.3996 | 7709.3968 | 0
| Information Technology | 5279.39 | 3441.4115 | 7022.1946 | 3919.5656 | 13860.2382 | 0
| Sub Total | 22286.05 | 16218.235 | 56977.7263 | 51662.3919 | 37225.4371 | 0
USMC Civilian MWR
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
MCCS Lodging
| Facilities and Improvements (Land and Structures) | 5162 | 6697 | 14961 | 16041 | 29004 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 1316 | 232 | 4700 | 5044 | 8300 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | 6478 | 6929 | 19661 | 21085 | 37304 | 0
USMC Supplemental Mission
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Air Force Military MWR
| Facilities and Improvements (Land and Structures) | 8306 | 71202 | 85371 | 101368 | 112684 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 72705 | 65272 | 66708 | 69510 | 73889 | 0
| Information Technology | 443 | 4664 | 4750 | 4837 | 4925 | 0
| Sub Total | 81454 | 141138 | 156829 | 175715 | 191498 | 0
Air Force Civilian MWR
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 7 | 232 | 67.5 | 77.3 | 96 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | 7 | 232 | 67.5 | 77.3 | 96 | 0
Air Force Lodging
| Facilities and Improvements (Land and Structures) | 7496 | 17467 | 68282 | 127287 | 192380 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 12373 | 11927 | 57563 | 64192 | 16870 | 0
| Information Technology | 747 | 50349 | 13911 | 16734 | 20435 | 0
| Sub Total | 20616 | 79743 | 139756 | 208213 | 229685 | 0
Air Force Supplemental Mission
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 | 0 | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 | 0 | 0
| Furnitures, Fixtures and Equipment | 30.9 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Sub Total | 30.9 | 0 | 0 | 0 | 0 | 0
Army Air Force Exchange Service
| Facilities and Improvements (Land and Structures) | 120000 | 110000 | 140000 | 140000 | 140000 | 0
| Major and Minor Construction | 0 | 0 | 0 | 0 |  | 0
| All Other Facility Investment | 0 | 0 | 0 | 0 |  | 0
| Furniture, Fixtures and Equipment | 4000 | 4000 | 4000 | 4000 | 4000 | 0
| Information Technology | 30000 | 30000 | 30000 | 30000 | 30000 | 0
| AAFES Total | 154000 | 144000 | 174000 | 174000 | 174000 | 0
Defense Commissary Agency DeCA
| Facilities and Improvements (Land and Structures) * | 146000 | 125641 | 167000 | 169700 | 173000 | 0
| Major and Minor Construction |  | 0 | 0 |  |  | 0
| All Other Facility Investment | 146000 | 125641 | 167000 | 169700 | 173000 | 0
| Furnitures, Fixtures and Equipment | 18000 | 11408 | 16000 | 16000 | 16000 | 0
| Information Technology | 38740 | 49032 | 47300 | 51100 | 54500 | 0
| Sub Total | 202740 | 186081 | 230300 | 236800 | 243500 | 0
| Equipment Maintenance/Lease/Rents (Not included above) | 18000 | 21810 | 22000 | 23000 | 24000 | 0
| DeCA Grand Total | 220740 | 207891 | 252300 | 259800 | 267500 | 0
TOTAL
| Facilities and Improvements (Land and Structures) | 483350.96 | 628873.8312 | 808111.4599 | 1170645.9526 | 1198437.7691 | 0
| Furniture, Fixtures and Equipment | 136449.6 | 189651.122 | 309702.607 | 287521.1365 | 239682.0722 | 0
| Information Technology | 90135.39 | 173419.8893 | 156613.9177 | 157108.8267 | 163581.188 | 0
| Grand Total | 709935.95 | 991944.8425 | 1274427.9846 | 1615275.9158 | 1601701.0293 | 0
Exchanges (NEXCOM, MCX, AAFES)
| Facilities and Improvements (Land and Structures) | 136342 | 135383.5568 | 175995.7457 | 181889.5259 | 235012.967 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | 28870 | 28681.573 | 38177.2894 | 36806.4369 | 42036.6754 | 0
| Information Technology | 36155 | 56889.4778 | 69723.7232 | 68373.2611 | 57621.9498 | 0
| Exchange Total | 201367 | 220954.6076 | 283896.7583 | 287069.2239 | 334671.5922 | 0
Military MWR
| Facilities and Improvements (Land and Structures) | 31134.96 | 104550.2744 | 176074.7142 | 197624.4267 | 199130.8021 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | 80137.7 | 96250.549 | 98622.8176 | 100961.3996 | 98955.3968 | 0
| Information Technology | 14493.39 | 17149.4115 | 20679.1946 | 17901.5656 | 28024.2382 | 0
| Military MWR Total | 125766.05 | 217950.235 | 295376.7263 | 316487.3919 | 326110.4371 | 0
Civilian MWR
| Facilities and Improvements (Land and Structures) | -109 | 0 | 0 | 0 | 0 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | -2191 | 90 | 38.5 | -71.7 | -57 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Civilian MWR Total | -2300 | 90 | 38.5 | -71.7 | -57 | 0
Lodging
| Facilities and Improvements (Land and Structures) | 170258 | 262964 | 288843 | 621228 | 591084 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | 19589 | 54382 | 157263 | 134236 | 83170 | 0
| Information Technology | 747 | 50349 | 18911 | 19734 | 23435 | 0
| Lodging Total | 190594 | 367695 | 465017 | 775198 | 697689 | 0
Supplemental Mission
| Facilities and Improvements (Land and Structures) | -275 | 335 | 198 | 204 | 210 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | -7956.1 | -1161 | -399 | -411 | -423 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Supplemental Mission Total | -8231.1 | -826 | -201 | -207 | -213 | 0

## (12) 5 Year Funding Report
Department of War
5 Year Funding Summary Data (PY2027 - 2031)
Commissary Surcharge, Nonappropriated Fund & Privately Financed Construction Program
($ Millions)
Note: - Please populate cells that are shaded light blue.
Total Shortfall | 0
Army MWR Shortfall | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Army Lodge Shortfall | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
AAFES Shortfall | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Navy MWR Shortfall | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
NEXCOM Hospitality Group (NHG) Lodging | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Navy Exchange (NEX) Shortfall | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
MCCS MWR/Exchange Shortfall | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Marine Corps Hospitality Services (MCHS) Lodging | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Air Force MWR Shortfall | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Air Force Lodging Shortfall | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
DeCA Shortfall | 0
($M)
FY | 2027 | 2028 | 2029 | 2030 | 2031 | Total
Capital Requirement | [5 empty] | 0
Surcharge Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0