## (0) NAFSGL Installation List
Service | Service Identifier | Installation Code (X XXXX) | Ins Code | Installation Name | State/Territory | Country | Feedback & Comments
Air Force | A | 0108 | A0108 | 319th Air Expeditionary Group | Expeditionary | Not Applicable | Project Number | Installation Name Missing | State/Country | Further Comments
Air Force | A | 0137 | A0137 | 332nd Balad | Expeditionary | Not Applicable
Air Force | A | 0123 | A0123 | 376th Air Expeditionary Wing | Expeditionary | Not Applicable
Air Force | A | 0114 | A0114 | 379th Air Expeditionary Wing | Expeditionary | Not Applicable
Air Force | A | 0124 | A0124 | 405th Air Expeditionary Wing | Expeditionary | Not Applicable
Air Force | A | 0125 | A0125 | 407th Air Expeditionary Group | Expeditionary | Not Applicable
Air Force | A | 0126 | A0126 | 438th Air Expeditionary Wing | Expeditionary | Not Applicable
Air Force | A | 0139 | A0139 | 455th Air Expeditionary Group | Expeditionary | Not Applicable
Air Force | A | 0127 | A0127 | 506th Air Expeditionary Group | Expeditionary | Not Applicable
Air Force | A | 0128 | A0128 | 64th Air Expeditionary Group | Expeditionary | Not Applicable
Army | R | 0265 | R0265 | Aberdeen Proving Ground | Maryland | United States
Army | R | 0266 | R0266 | Adelphi Laboratory Center | Maryland | United States
Air Force | A | 0231 | A0231 | AF FM Mngt Fund | Virtual | Not Applicable
Air Force | A | 0140 | A0140 | Air Combat Command - HQ | Virtual | Not Applicable
Air Force | A | 0228 | A0228 | Air Force 401K | Virtual | Not Applicable
Air Force | A | 0226 | A0226 | Air Force Capital Improvements | Virtual | Not Applicable
Air Force | A | 0225 | A0225 | Air Force Civilian Welfare | Virtual | Not Applicable
Air Force | A | 0203 | A0203 | Air Force District of Washington - HQ | Virtual | Not Applicable
Air Force | A | 0224 | A0224 | Air Force Fisher House | Virtual | Not Applicable
Air Force | A | 0230 | A0230 | Air Force Insurance Fund | Virtual | Not Applicable
Air Force | A | 0227 | A0227 | Air Force Lodging Fund | Virtual | Not Applicable
Air Force | A | 0222 | A0222 | Air Force Mission Essential Feeding Facility | Virtual | Not Applicable
Air Force | A | 0223 | A0223 | Air Force Morale, Welfare, and Recreation | Virtual | Not Applicable
Air Force | A | 0192 | A0192 | Air Force Reserve Command - HQ | Virtual | Not Applicable
Air Force | A | 0229 | A0229 | Air Force Retirement Fund | Virtual | Not Applicable
Air Force | A | 0171 | A0171 | Air Force Space Command - HQ | Virtual | Not Applicable
Air Force | A | 0143 | A0143 | Air Force Special Operations Command - HQ | Virtual | Not Applicable
Air Force | A | 0162 | A0162 | Air Mobility Command - HQ | Virtual | Not Applicable
Air Force | A | 0161 | A0161 | Air Transport Command - HQ | Virtual | Not Applicable
Air Force | A | 0132 | A0132 | Al Dhafra Air Base | OCONUS | United Arab Emirates
Air Force | A | 0134 | A0134 | Ali Al Salem Air Base | OCONUS | Kuwait
Air Force | A | 0163 | A0163 | Altus Air Force Base | Oklahoma | United States
Army | R | 0267 | R0267 | Anniston Army Depot | Alabama | United States
Army | R | DELETE | RDELETE | Area I | OCONUS | Korea, Republic of
Navy | N | 0570 | N0570 | Armed Forces Retirement Home Gulfport | Mississippi | United States
Navy | N | 0569 | N0569 | Armed Forces Retirement Home Washington | Virtual | Virtual
Air Force | A | 0210 | A0210 | Army and Air Force Exchange Service | Texas | United States
Army | R | DELETE | RDELETE | Army Civilian Welfare Fund | Virtual | Virtual
Army | R | DELETE | RDELETE | Army Lodging Fund | Texas | United States
Army | R | 0273 | R0273 | Army Recreation Machine Program, Germany | OCONUS | Germany
Army | R | 0269 | R0269 | Army Recreation Machine Program, Korea | OCONUS | Korea, Republic of
Army | R | DELETE | RDELETE | Army Rocky Mountain Arsenal | Colorado | United States
Army | R | DELETE | RDELETE | Army Solider Family Readiness Donations | Virginia | United States
Army | R | 0275 | R0275 | Army Ten-Miler | District of Columbia | United States
Air Force | A | 0184 | A0184 | Arnold Air Force Base | Tennessee | United States
Air Force | A | 0248 | A0248 | Aviano Air Base | OCONUS | Italy
Air Force | A | 0138 | A0138 | Baghdad | OCONUS | Iraq
Air Force | A | 0116 | A0116 | Barksdale Air Force Base | Louisiana | United States
Air Force | A | 0117 | A0117 | Beale Air Force Base | California | United States
Air Force | A | 0212 | A0212 | Bellows Air Force Station | Hawaii | United States
Army | R | 0354 | R0354 | Bluegrass Army Depot | Kentucky | United States
Air Force | A | 0174 | A0174 | Buckley Air Force Base | Colorado | United States
Air Force | A | 0234 | A0234 | Buechel Air Base | OCONUS | Germany
Marines | M | NEW | MNEW | Camp Courtney | OCONUS | Japan
Marines | M | 0421 | M0421 | Camp Elmore | Virginia | United States
Marines | M | NEW | MNEW | Camp Fuji | OCONUS | Japan
Marines | M | NEW | MNEW | Camp Hansen | OCONUS | Japan
Marines | M | NEW | MNEW | Camp Kinser | OCONUS | Japan
Navy | N | 0509 | N0509 | Camp Lemonnier; Djibouti | OCONUS | Djibouti
Army | R | 0278 | R0278 | Camp Mabry | Texas | United States
Marines | M | NEW | MNEW | Camp Schwab | OCONUS | Japan
Army | R | 0280 | R0280 | Camp Shelby Joint Forces Training Center | Mississippi | United States
Army | R | 0281 | R0281 | Camp Stanley | OCONUS | Korea, Republic of
Air Force | A | 0141 | A0141 | Cannon Air Force Base | New Mexico | United States
Air Force | A | 0129 | A0129 | Cape Cod Air Force Station | Massachusetts | United States
Army | R | 0282 | R0282 | Carlisle Barracks | Pennsylvania | United States
Air Force | A | 0130 | A0130 | Cavalier Air Force Station | North Dakota | United States
Air Force | A | 0131 | A0131 | Clear Air Force Station | Alaska | United States
Navy | N | 0563 | N0563 | CNIC Capital Fund | Virtual | Virtual
Navy | N | 0561 | N0561 | CNIC Child and Youth Programs | Virtual | Virtual
Navy | N | 0565 | N0565 | CNIC Civilian Morale, Welfare and Recreation | Virtual | Virtual
Navy | N | 0562 | N0562 | CNIC Family Readiness Warfighter & Family Support | Virtual | Virtual
Navy | N | 0571 | N0571 | CNIC Fisher Houses | Virtual | Virtual
Navy | N | 0587 | N0587 | CNIC IT Franchise Services | Virtual | Virtual
Navy | N | 0560 | N0560 | CNIC Morale, Welfare and Recreation | Virtual | Virtual
Navy | N | 0566 | N0566 | CNIC Navy Flying Club | Virtual | Virtual
Navy | N | 0567 | N0567 | CNIC Navy Gateway Inns & Suites | Virtual | Virtual
Navy | N | 0564 | N0564 | CNIC Navy Gateway Inns & Suites Capital Fund | Virtual | Virtual
Navy | N | NEW | NNEW | CNIC Navy Wounded Warrior - Safe Harbor | Virtual | Virtual
Navy | N | NEW | NNEW | CNIC Retirement Trust Agreement | Virtual | Virtual
Navy | N | 0589 | N0589 | CNIC Treasury | Virtual | Virtual
Army | R | 0283 | R0283 | Cold Regions Research and Engineering Laboratory (CRREL) | New Hampshire | United States
Air Force | A | 0153 | A0153 | Columbus Air Force Base | Mississippi | United States
Navy | N | 0462 | N0462 | Commander Fleet Activities Chinhae | OCONUS | Korea, Republic of
Navy | N | 0468 | N0468 | Commander Fleet Activities Okinawa | OCONUS | Japan
Navy | N | 0465 | N0465 | Commander Fleet Activities Sasebo | OCONUS | Japan
Navy | N | 0466 | N0466 | Commander Fleet Activities Yokosuka | OCONUS | Japan
Navy | N | 0536 | N0536 | Commander Navy Region Korea-Region | OCONUS | Virtual
Navy | N | 0541 | N0541 | Commander, Joint Region Marianas-Region | Virtual | Virtual
Navy | N | 0538 | N0538 | Commander, Navy Region Europe, Africa, Central Region | Virtual | Virtual
Navy | N | 0539 | N0539 | Commander, Navy Region Hawaii-Region | Virtual | Virtual
Navy | N | 0537 | N0537 | Commander, Navy Region Japan-Region | Virtual | Virtual
Navy | N | 0545 | N0545 | Commander, Navy Region Mid-Atlantic | Virginia | United States
Navy | N | 0542 | N0542 | Commander, Navy Region Northwest | Washington | United States
Navy | N | 0547 | N0547 | Commander, Navy Region Southeast-Region | Virtual | Virtual
Navy | N | 0544 | N0544 | Commander, Navy Region Southwest-Region | Virtual | Virtual
Army | R | DELETE | RDELETE | Consolidated Veterinary Funds - Cycle E | Texas | United States
Army | R | DELETE | RDELETE | Consolidated Veterinary Funds - Cycle R | Texas | United States
Navy | N | 0448 | N0448 | Construction Battalion Center Gulfport | Mississippi | United States
Air Force | A | 0106 | A0106 | Creech Air Force Base | Nevada | United States
Air Force | A | 0213 | A0213 | Daegu Air Base | OCONUS | Korea, Republic of
Air Force | A | 0103 | A0103 | Davis-Monthan Air Force Base | Arizona | United States
Army | R | 0286 | R0286 | Defense Depot Susquehanna, Pennsylvania (DDSP) | Pennsylvania | United States
Army | R | 0290 | R0290 | Defense Finance and Accounting Service (DFAS)-Indianapolis | Indiana | United States
Army | R | 0292 | R0292 | Defense General Supply Center (DGSC) Richmond | Virginia | United States
Army | R | NEW | RNEW | Defense General Supply, Belvoir | Virginia | United States
Army | R | 0287 | R0287 | Defense Intelligence Agency | District of Columbia | United States
Army | R | 0293 | R0293 | Defense Logistics Agency (DLA) Columbus | Ohio | United States
Army | R | 0295 | R0295 | Defense Logistics Services Center (DLSC) Battle Creek | Michigan | United States
Army | R | 0291 | R0291 | DFAS-Texarkana | Texas | United States
Army | R | 0288 | R0288 | Directorate of Emergency Services (DES) Fort Belvoir | Virginia | United States
Air Force | A | 0190 | A0190 | Dobbins Air Reserve Base | Georgia | United States
Army | R | 0296 | R0296 | DoD Concessions Committee | District of Columbia | United States
Air Force | A | 0164 | A0164 | Dover Air Force Base | Delaware | United States
Army | R | 0297 | R0297 | Dragon Hill Lodge | OCONUS | Korea, Republic of
Air Force | A | 0118 | A0118 | Dyess Air Force Base | Texas | United States
Army | R | 0299 | R0299 | Edelweiss Lodge and Resort | OCONUS | Germany
Air Force | A | 0178 | A0178 | Edwards Air Force Base | California | United States
Air Force | A | 0179 | A0179 | Eglin Air Force Base | Florida | United States
Air Force | A | 0191 | A0191 | Eglin Air Force Base | Florida | United States
Air Force | A | 0214 | A0214 | Eielson Air Force Base | Alaska | United States
Air Force | A | 0104 | A0104 | Ellsworth Air Force Base | South Dakota | United States
Army | R | 0300 | R0300 | Europe Statutory Accident Insurance Fund | OCONUS | Germany
Air Force | A | 0119 | A0119 | F. E. Warren Air Force Base | Wyoming | United States
Air Force | A | 0105 | A0105 | Fairchild Air Force Base | Washington | United States
Army | R | 0301 | R0301 | Fisher House | Texas | United States
Army | R | 0303 | R0303 | Fort Belvoir | Virginia | United States
Army | R | 0304 | R0304 | Fort Benning | Georgia | United States
Army | R | 0305 | R0305 | Fort Bliss | Texas | United States
Army | R | 0309 | R0309 | Fort Carson | Colorado | United States
Army | R | 0310 | R0310 | Fort Detrick | Maryland | United States
Army | R | 0311 | R0311 | Fort Devens | Massachusetts | United States
Army | R | 0313 | R0313 | Fort George G Meade | Maryland | United States
Army | R | 0316 | R0316 | Fort Hamilton | New York | United States
Army | R | 0317 | R0317 | Fort Hood | Texas | United States
Army | R | 0321 | R0321 | Fort Jackson | South Carolina | United States
Army | R | 0322 | R0322 | Fort Knox | Kentucky | United States
Army | R | 0329 | R0329 | Fort Rucker | Alabama | United States
Army | R | 0331 | R0331 | Fort Stewart-Hunter Army Airfield | Georgia | United States
Army | R | 0332 | R0332 | Fort Wainwright / USAG Alaska | Alaska | United States
Air Force | A | 0247 | A0247 | Ghedi Air Base | OCONUS | Italy
Air Force | A | 0208 | A0208 | Goodfellow Air Force Base | Texas | United States
Air Force | A | 0120 | A0120 | Grand Forks Air Force Base | North Dakota | United States
Air Force | A | 0194 | A0194 | Greater Pittsburgh Air Force Base | Pennsylvania | United States
Air Force | A | 0195 | A0195 | Grissom Air Force Base | New York | United States
Army | R | 0333 | R0333 | Hale Koa Hotel | Hawaii | United States
Air Force | A | 0180 | A0180 | Hanscom Air Force Base | Massachusetts | United States
Marines | M | 0441 | M0441 | Headquarters Marine Corps | Virginia | United States
Army | R | DELETE | RDELETE | Headquarters, Direct Reporting | Texas | United States
Air Force | A | 0186 | A0186 | Hill Air Force Base | Utah | United States
Air Force | A | 0142 | A0142 | Holloman Air Force Base | New Mexico | United States
Air Force | A | 0196 | A0196 | Homestead Air Reserve Base | Florida | United States
Air Force | A | 0233 | A0233 | HQ AFE | Virtual | Not Applicable
Army | R | 0336 | R0336 | HQ US Army (USAR) Japan | OCONUS | Japan
Army | R | 0262 | R0262 | HQ, Army Recreation Machine Program | Texas | United States
Army | R | 0294 | R0294 | HQ, Defense Logistics Agency | Virginia | Virtual
Army | R | 0337 | R0337 | HQ, Europe Oversight | OCONUS | Germany
Army | R | DELETE | RDELETE | HQ, Pacific Region | Hawaii | United States
Army | R | 0339 | R0339 | HQ, Surface Deployment & Distribution Center | Illinois | United States
Army | R | 0340 | R0340 | HQ, US Army South (USARSO) | Texas | United States
Army | R | 0341 | R0341 | Hunter Army Airfield | Georgia | United States
Air Force | A | 0144 | A0144 | Hurlburt Field | Florida | United States
Army | R | DELETE | RDELETE | IMCOM Central Region | Texas | United States
Army | R | 0344 | R0344 | IMCOM Europe Region | OCONUS | Germany
Army | R | DELETE | RDELETE | IMCOM HQ, Family and MWR Programs, G9 | Texas | United States
Army | R | DELETE | RDELETE | IMCOM Pacific Region | Hawaii | United States
Air Force | A | 0253 | A0253 | Incirlik Air Base | OCONUS | Turkey
Air Force | A | 0249 | A0249 | Izmir Air Station | OCONUS | Turkey
Army | R | DELETE | RDELETE | Japan | OCONUS | Japan
Navy | N | 0486 | N0486 | Joint Base Anacostia-Bolling | District of Columbia | United States
Air Force | A | 0204 | A0204 | Joint Base Andrews | Maryland | United States
Air Force | A | 0256 | A0256 | Joint Base Charleston | South Carolina | United States
Air Force | A | 0255 | A0255 | Joint Base Elmendorf-Richardson | Alaska | United States
Air Force | A | 0261 | A0261 | Joint Base Langley-Eustis | Virginia | United States
Army | R | 0348 | R0348 | Joint Base Lewis-McChord | Washington | United States
Air Force | A | 0254 | A0254 | Joint Base McGuire-Dix-Lakehurst | New Jersey | United States
Army | R | 0349 | R0349 | Joint Base Myer-Henderson Hall | Virginia | United States
Marines | M | 0426 | M0426 | Joint Base Myer-Henderson Hall (Henderson Hall) | Virginia | United States
Navy | N | 0489 | N0489 | Joint Base Pearl Harbor-Hickam | Hawaii | United States
Air Force | A | 0262 | A0262 | Joint Base San Antonio | Texas | United States
Navy | N | 0464 | N0464 | Joint Expeditionary Base Little Creek-Fort Story | Virginia | United States
Army | R | 0350 | R0350 | Joint Multinational Readiness Center (JMRC), Hohenfels | OCONUS | Germany
Air Force | A | 0217 | A0217 | Kadena Air Base | OCONUS | Japan
Air Force | A | 0263 | A0263 | Kandahar Airfield | OCONUS | Afghanistan
Air Force | A | 0154 | A0154 | Keesler Air Force Base | Mississippi | United States
Army | R | DELETE | RDELETE | Kilauea Military Camp | Hawaii | United States
Air Force | A | 0182 | A0182 | Kirtland Air Force Base | New Mexico | United States
Air Force | A | 0235 | A0235 | Kleine Brogel Air Base | OCONUS | Belgium
Army | R | 0335 | R0335 | Korea Region Oversight | OCONUS | Korea, Republic of
Air Force | A | 0218 | A0218 | Kunsan Air Base | OCONUS | Korea, Republic of
Air Force | A | 0170 | A0170 | Lajes Field | OCONUS | Portugal
Army | R | 0352 | R0352 | Landstuhl Regional Medical Center | OCONUS | Germany
Air Force | A | 0156 | A0156 | Laughlin Air Force Base | Texas | United States
Army | R | 0353 | R0353 | Letterkenny Army Depot | Pennsylvania | United States
Air Force | A | 0166 | A0166 | Little Rock Air Force Base | Arkansas | United States
Air Force | A | 0183 | A0183 | Los Angeles Air Force Base | California | United States
Air Force | A | 0146 | A0146 | Luke Air Force Base | Arizona | United States
Air Force | A | 0148 | A0148 | MacDill Air Force Base | Florida | United States
Air Force | A | 0121 | A0121 | Malmstrom Air Force Base | Montana | United States
Air Force | A | 0197 | A0197 | March Air Reserve Base | California | United States
Marines | M | 0419 | M0419 | Marine Barracks, Washington, D.C. | District of Columbia | United States
Marines | M | 0437 | M0437 | Marine Corps Air Ground Combat Center, Twentynine Palms | California | United States
Marines | M | 0435 | M0435 | Marine Corps Air Station Beaufort | South Carolina | United States
Marines | M | 0424 | M0424 | Marine Corps Air Station Cherry Point | North Carolina | United States
Marines | M | NEW | MNEW | Marine Corps Air Station Futenma | OCONUS | Japan
Marines | M | 0427 | M0427 | Marine Corps Air Station Iwakuni, Japan | OCONUS | Japan
Marines | M | 0429 | M0429 | Marine Corps Air Station Miramar | California | United States
Marines | M | 0430 | M0430 | Marine Corps Air Station New River | North Carolina | United States
Marines | M | 0438 | M0438 | Marine Corps Air Station Yuma | Arizona | United States
Marines | M | 0428 | M0428 | Marine Corps Base Camp Lejeune | North Carolina | United States
Marines | M | 0431 | M0431 | Marine Corps Base Camp Pendleton | California | United States
Marines | M | 0423 | M0423 | Marine Corps Base Camp Smedley D. Butler | OCONUS | Japan
Marines | M | 0425 | M0425 | Marine Corps Base Hawaii | Hawaii | United States
Marines | M | 0432 | M0432 | Marine Corps Base Quantico | Virginia | United States
Marines | M | 0434 | M0434 | Marine Corps Community Services (MCCS) South Carolina | South Carolina | United States
Marines | M | 0420 | M0420 | Marine Corps Logistics Base Albany | Georgia | United States
Marines | M | 0422 | M0422 | Marine Corps Logistics Base Barstow | California | United States
Marines | M | 0436 | M0436 | Marine Corps Recruit Depot Parris Island | South Carolina | United States
Marines | M | 0433 | M0433 | Marine Corps Recruit Depot San Diego | California | United States
Marines | M | 0440 | M0440 | Marine Corps Recruiting Command Garden City | New York | United States
Air Force | A | 0206 | A0206 | Maxwell Air Force Base | Alabama | United States
Army | R | 0355 | R0355 | McAlester Army Ammunition Plant | Oklahoma | United States
Air Force | A | 0111 | A0111 | McConnell Air Force Base | Kansas | United States
Air Force | A | 0185 | A0185 | Military Air Transport - HQ | Virtual | Not Applicable
Navy | N | 0588 | N0588 | Military Ticket Program | California | United States
Air Force | A | 0198 | A0198 | Minneapolis-St Paul Air Reserve Station | Minnesota | United States
Air Force | A | 0110 | A0110 | Minot Air Force Base | North Dakota | United States
Air Force | A | 0215 | A0215 | Misawa Air Base | OCONUS | Japan
Air Force | A | 0157 | A0157 | Moody Air Force Base | Georgia | United States
Air Force | A | 0246 | A0246 | Moron Air Base | OCONUS | Spain
Air Force | A | 0147 | A0147 | Mountain Home Air Force Base | Idaho | United States
Army | R | 0357 | R0357 | National Geospatial-Intelligence Agency (NGA) East | Maryland | United States
Army | R | 0358 | R0358 | National Geospatial-Intelligence Agency West | Missouri | United States
Army | R | 0359 | R0359 | National Ground Intelligence | Virginia | United States
Army | R | NEW | RNEW | National Security Agency | Maryland | United States
Air Force | A | 0239 | A0239 | NATO Air Base Geilenkirchen | OCONUS | Germany
Army | R | 0360 | R0360 | NATO School - Oberammergau | OCONUS | Germany
Navy | N | 0503 | N0503 | Naval Air Facility El Centro | California | United States
Navy | N | 0478 | N0478 | Naval Air Station Corpus Christi | Texas | United States
Navy | N | 0497 | N0497 | Naval Air Station Fallon | Nevada | United States
Navy | N | 0449 | N0449 | Naval Air Station Jacksonville | Florida | United States
Navy | N | 0474 | N0474 | Naval Air Station Joint Reserve Base Fort Worth | Texas | United States
Navy | N | 0480 | N0480 | Naval Air Station Joint Reserve Base New Orleans | Louisiana | United States
Navy | N | 0446 | N0446 | Naval Air Station Key West | Florida | United States
Navy | N | 0479 | N0479 | Naval Air Station Kingsville | Texas | United States
Navy | N | 0506 | N0506 | Naval Air Station Lemoore | California | United States
Navy | N | 0475 | N0475 | Naval Air Station Meridian | Mississippi | United States
Navy | N | 0451 | N0451 | Naval Air Station Oceana | Virginia | United States
Navy | N | 0482 | N0482 | Naval Air Station Patuxent River | Maryland | United States
Navy | N | 0476 | N0476 | Naval Air Station Pensacola | Florida | United States
Navy | N | 0493 | N0493 | Naval Air Station Whidbey Island | Washington | United States
Navy | N | 0477 | N0477 | Naval Air Station Whiting Field Milton | Florida | United States
Navy | N | 0504 | N0504 | Naval Air Weapons Station China Lake | California | United States
Navy | N | 0498 | N0498 | Naval Base Coronado | California | United States
Navy | N | NEW | NNEW | Naval Base Gueam | Guam | United States
Navy | N | 0492 | N0492 | Naval Base Kitsap | Washington | United States
Navy | N | 0514 | N0514 | Naval Base Point Loma | California | United States
Navy | N | 0540 | N0540 | Naval Base San Diego | California | United States
Navy | N | 0500 | N0500 | Naval Base Ventura County | California | United States
Navy | N | 0546 | N0546 | Naval District Washington-Region | Virtual | Virtual
Navy | N | 0513 | N0513 | Naval Ordnance Test Unit Cape Canaveral | Florida | United States
Navy | N | 0494 | N0494 | Naval Station Everett | Washington | United States
Navy | N | 0444 | N0444 | Naval Station Great Lakes | Illinois | United States
Navy | N | 0445 | N0445 | Naval Station Mayport | Florida | United States
Navy | N | 0460 | N0460 | Naval Station Newport | Rhode Island | United States
Navy | N | 0455 | N0455 | Naval Station Norfolk | Virginia | United States
Navy | N | 0516 | N0516 | Naval Submarine Base Kings Bay | Georgia | United States
Navy | N | 0463 | N0463 | Naval Submarine Base New London | Connecticut | United States
Navy | N | NEW | NNEW | Naval Support Activity Andersen | Guam | United States
Navy | N | 0485 | N0485 | Naval Support Activity Annapolis | Maryland | United States
Navy | N | 0484 | N0484 | Naval Support Activity Bethesda | Maryland | United States
Navy | N | 0443 | N0443 | Naval Support Activity Crane | Indiana | United States
Navy | N | 0456 | N0456 | Naval Support Activity Hampton Roads | Virginia | United States
Navy | N | 0457 | N0457 | Naval Support Activity Mechanicsburg | Pennsylvania | United States
Navy | N | 0505 | N0505 | Naval Support Activity Mechanicsburg Det Philadelphia | Pennsylvania | United States
Navy | N | 0481 | N0481 | Naval Support Activity Mid-South | Tennessee | United States
Navy | N | 0496 | N0496 | Naval Support Activity Monterey | California | United States
Navy | N | NEW | NNEW | Naval Support Activity Orlando | Florida | United States
Navy | N | 0447 | N0447 | Naval Support Activity Panama City | Florida | United States
Navy | N | 0458 | N0458 | Naval Support Activity Saratoga Springs | New York | United States
Navy | N | 0487 | N0487 | Naval Support Activity South Potomac Dahlgren | Virginia | United States
Navy | N | 0520 | N0520 | Naval Support Activity Wallops Island | Virginia | United States
Navy | N | 0483 | N0483 | Naval Support Facility Indian Head | Maryland | United States
Navy | N | NEW | NNEW | Naval Support Facility Redzikowo | OCONUS | PL
Navy | N | 0459 | N0459 | Naval Weapons Station Earle Colts Neck | New Jersey | United States
Navy | N | 0515 | N0515 | Naval Weapons Station Seal Beach | California | United States
Navy | N | 0450 | N0450 | Naval Weapons Station Yorktown | Virginia | United States
Navy | N | 0495 | N0495 | Navy Recreation Area Jim Creek | Washington | United States
Navy | N | 0491 | N0491 | Navy Recreation Area Pacific Beach | Washington | United States
Navy | N | 0507 | N0507 | Navy Recreation Area Solomons | Maryland | United States
Air Force | A | 0149 | A0149 | Nellis Air Force Base | Nevada | United States
Air Force | A | 0199 | A0199 | Niagara Falls Air Reserve Station | New York | United States
Navy | N | 0453 | N0453 | Norfolk Naval Shipyard | Virginia | United States
Navy | N | 0522 | N0522 | NSA Gaeta | OCONUS | Italy
Army | R | 0361 | R0361 | Office of Chief of Chaplains (OCCH) | District of Columbia | United States
Air Force | A | 0112 | A0112 | Offutt Air Force Base | Nebraska | United States
Air Force | A | 0220 | A0220 | Osan Air Base | OCONUS | Korea, Republic of
Navy | N | 0568 | N0568 | OSD CNIC Millington | Tennessee | United States
Air Force | A | 0211 | A0211 | Pacific Air Forces - HQ | Virtual | Not Applicable
Navy | N | 0490 | N0490 | Pacific Missile Range Facility Barking Sands | Hawaii | United States
Air Force | A | 0181 | A0181 | Patrick Air Force Base | Florida | United States
Air Force | A | 0205 | A0205 | Pentagon | Virginia | United States
Army | R | 0365 | R0365 | Pentagon Athletic Center (PAC) | District of Columbia | United States
Air Force | A | 0173 | A0173 | Peterson Air Force Base | Colorado | United States
Air Force | A | 0200 | A0200 | Portland International Airport Air Guard Station | Oregon | United States
Navy | N | 0461 | N0461 | Portsmouth Naval Shipyard | New Hampshire | United States
Army | R | NEW | RNEW | Pueblo Army Depot | Colorado | United States
Air Force | A | 0237 | A0237 | Ramstein Air Base | OCONUS | Germany
Army | R | 0366 | R0366 | Red River Army Depot | Texas | United States
Army | R | 0367 | R0367 | Redstone Arsenal | Alabama | United States
Air Force | A | 0145 | A0145 | Reserved | Not Applicable | Not Applicable
Air Force | A | 0155 | A0155 | Reserved | Not Applicable | Not Applicable
Air Force | A | 0158 | A0158 | Reserved | Not Applicable | Not Applicable
Air Force | A | 0165 | A0165 | Reserved | Not Applicable | Not Applicable
Air Force | A | 0167 | A0167 | Reserved | Not Applicable | Not Applicable
Air Force | A | 0177 | A0177 | Reserved | Not Applicable | Not Applicable
Air Force | A | 0209 | A0209 | Reserved | Not Applicable | Not Applicable
Air Force | A | 0221 | A0221 | Reserved | Not Applicable | Not Applicable
Air Force | A | 0187 | A0187 | Robins Air Force Base | Georgia | United States
Army | R | 0369 | R0369 | Rock Island Corps of Engineers (COE) | Illinois | United States
Air Force | A | 0244 | A0244 | Royal Air Force Alconbury, Royal Air Force Molesworth, Royal Air Force Upwood | OCONUS | United Kingdom
Air Force | A | 0243 | A0243 | Royal Air Force Croughton | OCONUS | United Kingdom
Air Force | A | 0245 | A0245 | Royal Air Force Fairford | OCONUS | United Kingdom
Air Force | A | 0241 | A0241 | Royal Air Force Lakenheath | OCONUS | United Kingdom
Air Force | A | 0240 | A0240 | Royal Air Force Menwith Hill | OCONUS | United Kingdom
Air Force | A | 0242 | A0242 | Royal Air Force Mildenhall | OCONUS | United Kingdom
Army | R | 0371 | R0371 | San Joaquin | California | United States
Air Force | A | 0172 | A0172 | Schriever Air Force Base | Colorado | United States
Air Force | A | 0169 | A0169 | Scott Air Force Base | Illinois | United States
Air Force | A | 0150 | A0150 | Seymour Johnson Air Force Base | North Carolina | United States
Army | R | 0372 | R0372 | Shades of Green | Florida | United States
Army | R | 0373 | R0373 | Sharpe Army Depot | California | United States
Air Force | A | 0151 | A0151 | Shaw Air Force Base | South Carolina | United States
Air Force | A | 0159 | A0159 | Sheppard Air Force Base | Texas | United States
Army | R | 0374 | R0374 | Sierra Army Depot | California | United States
Navy | N | 0521 | N0521 | Singapore Area Coordinator-Installation | OCONUS | Singapore
Navy | N | 0543 | N0543 | Singapore Area Coordinator-Region | Virtual | Virtual
Navy | N | NEW | NNEW | Singapore Naval Base | OCONUS | Singapore
Army | R | 0375 | R0375 | Soto Cano Air Base | OCONUS | Honduras
Air Force | A | 0238 | A0238 | Spangdahlem Air Base | OCONUS | Germany
Army | R | DELETE | RDELETE | Stars & Stripes Europe | OCONUS | Germany
Army | R | 0378 | R0378 | Stars & Stripes Pacific | OCONUS | Japan
Army | R | 0376 | R0376 | Stars & Stripes, HQ | District of Columbia | United States
Air Force | A | 0252 | A0252 | Stavanger Air Base | OCONUS | Norway
Army | R | 0379 | R0379 | Texas Roadhouse | Texas | United States
Army | R | 0380 | R0380 | The Judge Advocate General's Legal Center and School | Virginia | United States
Army | R | 0320 | R0320 | The National Training Center and Fort Irwin | California | United States
Air Force | A | 0176 | A0176 | Thule Air Base | OCONUS | Greenland
Air Force | A | 0188 | A0188 | Tinker Air Force Base | Oklahoma | United States
Army | R | 0381 | R0381 | Tobyhanna Army Depot | Pennsylvania | United States
Army | R | 0382 | R0382 | Tooele Army Depot | Utah | United States
Army | R | NEW | RNEW | Torri Station Army Base | OCONUS | Japan
Air Force | A | 0152 | A0152 | Travis Air Force Base | California | United States
Army | R | 0383 | R0383 | Tripler Army Medical Center | Hawaii | United States
Air Force | A | 0175 | A0175 | Tyndall Air Force Base | Florida | United States
Air Force | A | 0207 | A0207 | U.S. Air Force Academy | Colorado | United States
Army | R | 0362 | R0362 | U.S. Army - Parks Reserve Forces Training Area (Camp Parks) | California | United States
Army | R | 0412 | R0412 | U.S. Army Chaplain Center and School | South Carolina | United States
Army | R | 0289 | R0289 | U.S. Army Detroit Arsenal | Michigan | United States
Army | R | 0298 | R0298 | U.S. Army Dugway Proving Ground | Utah | United States
Army | R | 0306 | R0306 | U.S. Army Fort Bragg | North Carolina | United States
Army | R | 0307 | R0307 | U.S. Army Fort Buchanan Puerto Rico | Puerto Rico | United States
Army | R | 0308 | R0308 | U.S. Army Fort Campbell | Kentucky | United States
Army | R | 0312 | R0312 | U.S. Army Fort Drum | New York | United States
Army | R | 0314 | R0314 | U.S. Army Fort Gordon | Georgia | United States
Army | R | 0318 | R0318 | U.S. Army Fort Huachuca | Arizona | United States
Army | R | 0323 | R0323 | U.S. Army Fort Leavenworth | Kansas | United States
Army | R | 0325 | R0325 | U.S. Army Fort Leonard Wood | Missouri | United States
Army | R | 0326 | R0326 | U.S. Army Fort McCoy | Wisconsin | United States
Army | R | 0328 | R0328 | U.S. Army Fort Riley | Kansas | United States
Army | R | 0386 | R0386 | U.S. Army Garrison Ansbach | OCONUS | Germany
Army | R | DELETE | RDELETE | U.S. Army Garrison Bamberg | OCONUS | Germany
Army | R | 0388 | R0388 | U.S. Army Garrison Baumholder | OCONUS | Germany
Army | R | 0389 | R0389 | U.S. Army Garrison Bavaria | OCONUS | Germany
Army | R | 0390 | R0390 | U.S. Army Garrison Benelux | OCONUS | Belgium
Army | R | 0391 | R0391 | U.S. Army Garrison Brussels | OCONUS | Belgium
Army | R | 0279 | R0279 | U.S. Army Garrison Camp Red Cloud | OCONUS | Korea, Republic of
Army | R | 0276 | R0276 | U.S. Army Garrison Casey | OCONUS | Korea, Republic of
Army | R | 0392 | R0392 | U.S. Army Garrison Daegu | OCONUS | Korea, Republic of
Army | R | 0315 | R0315 | U.S. Army Garrison Fort Greely | Alaska | United States
Army | R | 0319 | R0319 | U.S. Army Garrison Fort Hunter Liggett | California | United States
Army | R | 0324 | R0324 | U.S. Army Garrison Fort Lee | Virginia | United States
Army | R | 0330 | R0330 | U.S. Army Garrison Fort Sill | Oklahoma | United States
Army | R | 0393 | R0393 | U.S. Army Garrison Garmisch | OCONUS | Germany
Army | R | 0394 | R0394 | U.S. Army Garrison Hawaii | Hawaii | United States
Army | R | 0395 | R0395 | U.S. Army Garrison Hohenfels | OCONUS | Germany
Army | R | 0277 | R0277 | U.S. Army Garrison Humphreys | OCONUS | Korea, Republic of
Army | R | 0406 | R0406 | U.S. Army Garrison Italy | OCONUS | Italy
Army | R | 0396 | R0396 | U.S. Army Garrison Japan | OCONUS | Japan
Army | R | 0409 | R0409 | U.S. Army Garrison Kwajalein-Atoll | OCONUS | Republic of the Marshall Islands
Army | R | 0397 | R0397 | U.S. Army Garrison Livorno | OCONUS | Italy
Army | R | 0398 | R0398 | U.S. Army Garrison Miami | Florida | United States
Army | R | 0399 | R0399 | U.S. Army Garrison Okinawa | OCONUS | Japan
Army | R | 0363 | R0363 | U.S. Army Garrison Picatinny Arsenal | New Jersey | United States
Army | R | 0364 | R0364 | U.S. Army Garrison Pine Bluff Arsenal | Arkansas | United States
Army | R | 0400 | R0400 | U.S. Army Garrison Pohakuloa Training Area | Hawaii | United States
Army | R | 0401 | R0401 | U.S. Army Garrison Presidio Of Monterey | California | United States
Army | R | 0402 | R0402 | U.S. Army Garrison Rheinland-Pfalz | OCONUS | Germany
Army | R | 0368 | R0368 | U.S. Army Garrison Rock Island Arsenal | Illinois | United States
Army | R | 0403 | R0403 | U.S. Army Garrison Schinnen | OCONUS | Netherlands
Army | R | DELETE | RDELETE | U.S. Army Garrison Schweinfurt | OCONUS | Germany
Army | R | 0405 | R0405 | U.S. Army Garrison Stuttgart | OCONUS | Germany
Army | R | 0407 | R0407 | U.S. Army Garrison Wiesbaden | OCONUS | Germany
Army | R | 0408 | R0408 | U.S. Army Garrison Yongsan | OCONUS | Korea, Republic of
Army | R | 0418 | R0418 | U.S. Army Garrison Yuma Proving Ground | Arizona | United States
Army | R | 0327 | R0327 | U.S. Army JRTC and Fort Polk | Louisiana | United States
Army | R | 0356 | R0356 | U.S. Army Natick Soldier Systems Center | Massachusetts | United States
Army | R | 0410 | R0410 | U.S. Army Publications Distribution Center | Missouri | United States
Army | R | 0411 | R0411 | U.S. Military Academy at West Point | New York | United States
Navy | N | 0529 | N0529 | U.S. National Support Element Latina | OCONUS | Italy
Navy | N | 0526 | N0526 | U.S. National Support Element Lisbon | OCONUS | Portugal
Navy | N | 0527 | N0527 | U.S. National Support Element Madrid | OCONUS | Spain
Navy | N | 0528 | N0528 | U.S. National Support Element Valencia | OCONUS | Spain
Navy | N | 0533 | N0533 | U.S. National Support Element, Fujurah | OCONUS | United Arab Emirates
Navy | N | 0531 | N0531 | U.S. National Support Element, Isa | OCONUS | Bahrain
Navy | N | 0532 | N0532 | U.S. National Support Element, Jebel Ali | OCONUS | Bahrain
Navy | N | 0573 | N0573 | U.S. Naval Academy Business Services Division | Virtual | Virtual
Navy | N | 0575 | N0575 | U.S. Naval Academy Candidate Guidance Fund | Virtual | Virtual
Navy | N | NEW | NNEW | U.S. Naval Academy Midshipmen Rations | Virtual | Virtual
Navy | N | 0574 | N0574 | U.S. Naval Academy Midshipmen Welfare Fund | Virtual | Virtual
Navy | N | 0467 | N0467 | U.S. Naval Air Facility Atsugi | OCONUS | Japan
Navy | N | 0470 | N0470 | U.S. Naval Air Station Sigonella | OCONUS | Italy
Navy | N | 0523 | N0523 | U.S. Naval Joint Services Activity The New Sanno | OCONUS | Japan
Navy | N | 0442 | N0442 | U.S. Naval Station Guantanamo Bay | OCONUS | Cuba
Navy | N | 0469 | N0469 | U.S. Naval Station Rota | OCONUS | Spain
Navy | N | 0508 | N0508 | U.S. Naval Support Activity Bahrain | OCONUS | Bahrain
Navy | N | 0471 | N0471 | U.S. Naval Support Activity Naples | OCONUS | Italy
Navy | N | 0518 | N0518 | U.S. Naval Support Activity Souda Bay | OCONUS | Greece
Navy | N | 0535 | N0535 | U.S. Naval Support Facility Deveselu | OCONUS | Romania
Navy | N | 0511 | N0511 | U.S. Naval Support Facility Diego Garcia | OCONUS | United Kingdom
Army | R | 0384 | R0384 | Umatilla Chemical Depot | Oregon | United States
Army | R | 0385 | R0385 | Uniformed Services University of Health Science (USUHS) | Maryland | United States
Air Force | A | 0135 | A0135 | United States Military Training Mission, Riyadh | OCONUS | Saudi Arabia
Army | R | DELETE | RDELETE | US Army Europe (USAEUR) Vehicle Registry | Virtual | Virtual
Army | R | 0302 | R0302 | US Army Garrison Fort A.P. Hill | Virginia | United States
Army | R | DELETE | RDELETE | US Army Installation Command (IMCOM) Atlantic Region | Texas | United States
Navy | N | 0555 | N0555 | USS Abraham Lincoln (CVN-72) | Ship | United States
Navy | N | 0552 | N0552 | USS Carl Vinson (CVN 70) | Ship | United States
Navy | N | 0548 | N0548 | USS Dwight D. Eisenhower (CVN 69) | Ship | United States
Navy | N | 0558 | N0558 | USS George H. W. Bush (CVN 77) | Ship | United States
Navy | N | 0551 | N0551 | USS George Washington (CVN 73) | Ship | United States
Navy | N | 0559 | N0559 | USS Gerald R. Ford (CVN 78) | Ship | United States
Navy | N | 0556 | N0556 | USS Harry S Truman (CVN 75) | Ship | United States
Navy | N | 0550 | N0550 | USS John C Stennis (CVN 74) | Ship | United States
Navy | N | 0553 | N0553 | USS Nimitz (CVN 68) | Ship | United States
Navy | N | 0557 | N0557 | USS Ronald Reagan (CVN 76) | Ship | United States
Navy | N | 0549 | N0549 | USS Theodore Roosevelt (CVN 71) | Ship | United States
Air Force | A | 0160 | A0160 | Vance Air Force Base | Oklahoma | United States
Air Force | A | 0115 | A0115 | Vandenberg Air Force Base | California | United States
Air Force | A | 0236 | A0236 | Vogelweh/Sembach | OCONUS | Germany
Navy | N | 0488 | N0488 | Washington Navy Yard | District of Columbia | United States
Army | R | 0414 | R0414 | Watervliet Arsenal | New York | United States
Air Force | A | 0201 | A0201 | Westover Air Reserve Base | Massachusetts | United States
Army | R | 0415 | R0415 | White Sands Missile Range | New Mexico | United States
Air Force | A | 0122 | A0122 | Whiteman Air Force Base | Missouri | United States
Army | R | 0416 | R0416 | William Beaumont Army Medical Center | Texas | United States
Air Force | A | 0189 | A0189 | Wright-Patterson Air Force Base | Ohio | United States
Army | R | 0417 | R0417 | Yakima Training Center | Washington | United States
Air Force | A | 0216 | A0216 | Yokota Air Base | OCONUS | Japan
Air Force | A | 0202 | A0202 | Youngstown Air Reserve Station | Ohio | United States

## Data Elements (hidden)
Component | Scope Type | State/Country | Funding | Program | Construction Classifications
USAF | SM | AL | SC | Commissary | Administrative Office/Supply Center
USA | Bays | AK | NAF | Exchange | Aquatic Training Facility/Bathhouse for military training, physical fitness, combat training and/or therapy
USN | Cabins | AZ | PF | Lodging | Auditorium/Multipurpose Theater
USMC | Connection | AR | APF | MWR | Gymnasium/Fieldhouse/Physical Activities
| Cottages | CA |  | Privately Financed | Library
| Each | CO |  |  | Playing Courts and Fields (associated with physical conditioning)
| Holes | CT |  |  | Recreation Center/Day Room/Multipurpose Recreational Facility (Military Personnel)
| Islands | DE |  |  | Park and Picnic Areas
| Lanes | FL |  |  | Military and Family Assistance Centers
| Pads | GA |  |  | Arts and Crafts/Skill Development
| Pumps | HI |  |  | Automotive Skill Development Center
| Rooms | ID |  |  | Campgrounds
| Sites | IL |  |  | Outdoor Recreation Pavilion
| Slips | IN |  |  | Playing Courts and Fields
| Spaces | IA |  |  | Recreation Equipment Issue/Checkout Facility
| Units | KS |  |  | Recreation Swimming Pools/Bathhouse/Aquatic Centers
| Well | KY |  |  | Youth Centers/Courts/Playing Fields – OCONUS
|  | LA |  |  | Youth Centers/Courts/Playing Fields – CONUS
|  | ME |  |  | Bowling Centers (16 lanes or less)
|  | MD |  |  | Child Development Centers
|  | MA |  |  | Marinas without Resale or Private Berthing
|  | MI |  |  | Information, Tickets and Tours Facilities
|  | MN |  |  | Service Member Techno-Activites Center
|  | MS |  |  | Community Activity and Recreation Centers (Military and Family Members)
|  | MO |  |  | Aero Club
|  | MT |  |  | Amateur Radio Facility
|  | NE |  |  | Joint Service and Military Service Recreation Centers (accommodations/dining and resale facilities)
|  | NV |  |  | Bandstand
|  | NH |  |  | Bathhouse
|  | NJ |  |  | Bowling Centers (more than 16 lanes)
|  | NM |  |  | Car Wash
|  | NY |  |  | Golf Course/Facility
|  | NC |  |  | Marinas/Boathouse/Watercraft Storage
|  | ND |  |  | Open Messes/Military Clubs/Food and Beverage
|  | OH |  |  | Other MWR Resale Outlets
|  | OK |  |  | Outdoor Theater
|  | OR |  |  | Recreational Lodging
|  | PA |  |  | Recreational Water Parks
|  | PR |  |  | Riding Stable
|  | RI |  |  | Rod and Gun Club
|  | SC |  |  | Recreational Vehicle (RV) Parks and Storage Lots
|  | SD |  |  | Skating Rink (Ice or Roller)
|  | TN |  |  | Open Messes/Military Clubs/Food and Beverage
|  | TX |  |  | Other MWR Resale Outlets
|  | UT |  |  | Outdoor Theater
|  | VT |  |  | Recreational Lodging
|  | VA |  |  | Recreational Water Parks
|  | WA |  |  | Riding Stable
|  | WV |  |  | Rod and Gun Club
|  | WI |  |  | Recreational Vehicle (RV) Parks and Storage Lots
|  | WY |  |  | Skating Rink (Ice or Roller)
|  | Afghanistan |  |  | PCS Lodging Facility (in support of official PCS travel, operated as MWR Category C)
|  | Bahrain |  |  | Equipment Rental
|  | Belgium |  |  | Animal Kennels and Care
|  | Cuba |  |  | Exchange Logistical, Administrative, Storage and Maintenance Facilities outside the United States
|  | Djibouti |  |  | Exchange Facilities required in areas of military conflict, wartime deployments, and in support of contingency, humanitarian, and peacekeeping operations
|  | Germany |  |  | Exchange Facilities required as integral parts of air terminal, hospital, housing, or other MILCON projects
|  | Greece |  |  | Exchange operated laundries and dry cleaning plants, bakeries, dairies, or similar facilities in support of a military mission, wartime deployments, and in support of contingency, humanitarian, and peacekeeping operations
|  | Greenland |  |  | Retail Stores, Malls, and Shopping Centers
|  | Guam |  |  | Convenience Stores
|  | Honduras |  |  | Automotive repair, gas, and service stations
|  | Iraq |  |  | Packaged beverage stores
|  | Italy |  |  | Laundry and dry cleaning
|  | Japan |  |  | Self-storage
|  | Korea, Republic of |  |  | Name Brand Fast Food
|  | Kuwait |  |  | All Other Exchange Facilities
|  | Marshall Islands |  |  | Exchange Category C – All Facilities
|  | Netherlands |  |  | Category A – TDY Lodging Facility (in support of official TDY travel)
|  | Norway |  |  | Category A – PCS Lodging Facility (in support of official PCS travel)
|  | Portugal |  |  | Category B – Stars & Stripes Facilities
|  | Qatar |  |  | Special Purpose Funds: Category C – All Facilities
|  | Romania |  |  | Commissary Store
|  | Saudi Arabia |  |  | Commissary Administrative Offices
|  | Singapore |  |  | Commissary Central Product Processing
|  | Spain |  |  | Banks
|  | Turkey |  |  | Credit Unions
|  | United Arab Emirates |  |  | Family Assistance Centers
|  | United Kingdom |  |  | Museums
Monuments and Museums
Service Academy Extra-Curricular Activities
Thrift Shop
Supplemental Mission Funds: Category C – All Facilities

## (1) Major Const Proj Sum Data
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
FY 2024 Major Construction Program Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0). The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoD Facility Analysis Category Code. Please make sure to use the 4 digit code.
(5) | Input contracting method used as defined in Enclosure 2 of DoDI 7700.18 of December 15, 2004: Design/Build (E2.1.18), Turnkey (E.2.1.30) or traditional Design-Bid-Build.
Number of Projects | Component | State / Country | Installation (1) | Installation Code (2) | Project Title | Project Number (3) | DoD FAC Code (4) | Scope | Scope Type | Construction Cost ($000) | Project Cost ($000) | Design Stage (%) | NPV ($000) | IRR (%) | Payback Period (Years) | Contract Award Date (MM/DD/YY) | Expected Completion Date (MM/DD/YY) | Funding | Program | Design/Build, Turnkey, or Design/Bid/Build (5) | Cat (A,B,C) | Design Cost | Equipment Cost
Policy Requiring Waiver:
1 | In accordance with DoD Instruction 1015.15, Lodging Program Resource Management, Temporary Duty (TDY) lodging facilities are to be constructed with appropriated
funds unless the Secretary of the Military Department or the Military Service headquarters designee concerned has certified that APF is unavailable recognizing
that the waiver of fund source will create higher NAF expenses and possibly higher lodging service charges.
2 | In accordance with DOD Instruction 1015.15, Procedures for Establishment, Management, and Control of Nonappropriated Fund Instrumentalities and Financial
Management of Supporting Resources, appropriated funds are to be used for youth centers, courts, and playing fields outside the continental U.S. unless the
Secretary of the Military Department concerned has certified that APF is unavailable.
3 | In accordance with DOD Instruction 1330.21, Armed Services Exchange Regulations (ASER), when establishing name-brand fast-food (NBFF) operations, concession
operations are preferred in the United States. Notice of deviations from the preferred method that results in major construction projects shall accompany the
major construction program and shall include the evaluation of economic and non-economic factors.
4 | In accordance with DOD Instruction 7700.18, Commissary Surcharge, Nonappropriated Fund (NAF), and Privately Financed Construction Report Procedures, project
design shall be 35 percent complete when submitted to USD(P&R) except design/build or turnkey contracts, which must be at least 15 percent complete.
5 | In accordance with the PDUSD(P&R) December 4, 2007 memorandum, the Military Department may request a deviation or exception to use nonappropriated funds in lieu
of appropriations when all of the following criteria are satisfied: (1) the Military Department included the project in its Military Construction (MILCON)
(major and minor construction) or APF modernization budget submission to the USD(C); (2) the project was not included in the President's Budget submission to
the Congress or was not approved by the Congress; (3) failure to build the facility will seriously impact quality of life of military personnel and their
families; (4) the Military Service certifies that the project is of higher priority than all other non-funded NAF construction (major and minor) and
modernization requirements; and (5) the Military Department endorses the use of NAF.

## (2) Major Proj Req Waivers
ENCLOSURE 4
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
Major Projects Requiring Waivers
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation Code corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoD Facility Analysis Category Code. Please make sure to use the 4 digit code.
(5) | Please specify the policy requiring waiver in the table below.
Number of Projects | Component | State / Country | Installation (1) | Installation Code (2) | Project Title | Project Number (3) | DoD FAC Code (4) | Project / Cost Avoidance ($000) | Note (5)
Policy Requiring Waiver:
1 | In accordance with DoD Instruction 1015.15, Lodging Program Resource Management, Temporary Duty (TDY) lodging facilities are to be constructed with appropriated
funds unless the Secretary of the Military Department or the Military Service headquarters designee concerned has certified that APF is unavailable recognizing
that the waiver of fund source will create higher NAF expenses and possibly higher lodging service charges.
2 | In accordance with DOD Instruction 1015.15, Procedures for Establishment, Management, and Control of Nonappropriated Fund Instrumentalities and Financial
Management of Supporting Resources, appropriated funds are to be used for youth centers, courts, and playing fields outside the continental U.S. unless the
Secretary of the Military Department concerned has certified that APF is unavailable.
3 | In accordance with DOD Instruction 1330.21, Armed Services Exchange Regulations (ASER), when establishing name-brand fast-food (NBFF) operations, concession
operations are preferred in the United States. Notice of deviations from the preferred method that results in major construction projects shall accompany the
major construction program and shall include the evaluation of economic and non-economic factors.
4 | In accordance with DOD Instruction 7700.18, Commissary Surcharge, Nonappropriated Fund (NAF), and Privately Financed Construction Report Procedures, project
design shall be 35 percent complete when submitted to USD(P&R) except design/build or turnkey contracts, which must be at least 15 percent complete.
5 | In accordance with the PDUSD(P&R) December 4, 2007 memorandum, the Military Department may request a deviation or exception to use nonappropriated funds in lieu
of appropriations when all of the following criteria are satisfied: (1) the Military Department included the project in its Military Construction (MILCON)
(major and minor construction) or APF modernization budget submission to the USD(C); (2) the project was not included in the President's Budget submission to
the Congress or was not approved by the Congress; (3) failure to build the facility will seriously impact quality of life of military personnel and their
families; (4) the Military Service certifies that the project is of higher priority than all other non-funded NAF construction (major and minor) and
modernization requirements; and (5) the Military Department endorses the use of NAF.

## (3) Minor Const Proj Sum Data
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
Minor Construction Program Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0). The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoD Facility Analysis Category Code. Please make sure to use the 4 digit code.
Number of Projects | Component | State / Country | Installation (1) | Installation Code (2) | Project Title | Project Number (3) | DoD FAC Code (4) | Construction Cost ($000) | Project Cost ($000) | Scope | Scope Type | Contract Award Date (MM/DD/YY) | Funding | Design Cost | Equipment Cost

## (4) Cancelled Const Proj Sum
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
Cancelled Major Construction Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoD Facility Analysis Category Code. Please make sure to use the 4 digit code.
Number of Projects | Component | FY Approved | State / Country | Installation (1) | Installation Code (2) | Project Title | Project Number (3) | DoD FAC Code (4) | Project Cost ($000) | Rationale for Cancellation
1
2
3
4
5
6
7
8
9
10
11
*** A summary paragraph shall be provided describing the rationale for each canceled project. ****
Note 1 | COVID-19 financial solvency of the funds

## (5) Delayed Contract Award Sum
ENCLOSURE 3
Department of Defense
FY2023 Commissary Surcharge, Nonappropriated Fund, and Privately Financed Construction
Delayed Contract Award Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation Code corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoD Facility Analysis Category Code. Please make sure to use the 4 digit code.
| Component | FY Approved | State / Country | Installation (1) | Installation Code (2) | Project Title | Project Number (3) | DoD FAC Code (4) | Construction Cost ($000) | Project Cost ($000) | Estimated Contract Award Date (MMM-YY) | Rationale for Delay
Project is 100% Designed but is being reprogrammed due to market conditions. AAFES hasn't received APF for roof repairs, HVAC repairs, the mass notification system and APF share of the Military Clothing. APF is now expected in FY24. In the meantime, AAFES is re-evaluating the project scope and costs.
Construction agent took a year to award Design MOD.
Project was shifted to FY24 due to Quality of Life projects taking priority. Brought back to FY23 due to significant need since old facility has been demolished.
The German Bauamt has first right of refusal to design and award the construction contract. After a lengthy review, they decided not to take the project on, which delayed the USA Corps of Engineers from awarding the design contract.
Project was originally submitted in F17 but Re-reported in FY19. Scope increased by 10.2% and costs by 18% over what was Re-Reported and approved by OSD in FY19. The Exchange changed a food concept from an Arby’s to a Popeyes to increase sales and eanings. The German Design Agency (Bauamt) then identified additional fire code requirements for a partial basement, fire control room and other technical rooms. Dealys are due to additional unexpected Bauamt delays in designing the project and readying for solicitation. It also took time to obtain brand (Popeye's) approvals. The Bauamt has identified contamination of the site and the base is programming funding for remediation of the site. Anticipated award is now Summer 2024.
APF Delays in executing the road reconfiguration, utility relocations, and site demolition have delayed AAFES (NAF) project execution.
In the FY21 Report, AAFES reported that the vendor selected for the Theater had backed out of the deal and that we had executed a contract with a new theater vendor. Rising costs from Hurricane Michael recovery and tariffs had also impacted projects in this area. AAFES then worked on a contract, drawings, solicitation and award with a new theater tenant (SE Cinema) with an estimated award of Jun 2021. However, SE Cinema subsequently backed out of the deal because of Covid. AAFES has now signed a new contract with CW Theaters. The estimated award is now 01 Oct 2022.
Delay in coordination with Navy along with COVID. Design contract currently underway.
In the FY21 Report, AAFES reported that the Dual Food was dependent upon the JBLM DPW bringing utilities and a new road to the site. AAFES also required the garrison to demolish the existing Burger King. AAFES also re-reported the project for cost increases exceeding 25% as a result of the five year delay. The project will not be awarded before the Garrison obtains APF for the new road and utilities. The three-year site approval has expired and AAFES is requesting a new site approval. The estimated award is TBD, most likely no earlier than Jun 2023.
[6 empty] | TOTAL |  |  | 0 | 0
*** A summary paragraph shall be provided describing the rationale for each delayed project. ****
Note 1 | Project was originally submitted in F17 but Re-reported in FY19. Scope increased by 10.2% and costs by 18% over what was Re-Reported and approved by OSD in FY19. The Exchange changed a food concept from an Arby’s to a Popeyes to increase sales and eanings. The German Design Agency (Bauamt) then identified additional fire code requirements for a partial basement, fire control room and other technical rooms. Dealys are due to additional unexpected Bauamt delays in designing the project and readying for solicitation. It also took time to obtain brand (Popeye's) approvals. The Bauamt has identified contamination of the site and the base is programming funding for remediation of the site. Anticipated award is now Summer 2024.
Note 2 | Project is 100% Designed but is being reprogrammed due to market conditions. AAFES hasn't received APF for roof repairs, HVAC repairs, the mass notification system and APF share of the Military Clothing. APF is now expected in FY24. In the meantime, AAFES is re-evaluating the project scope and costs.
Note 3 | APF Delays in executing the road reconfiguration, utility relocations, and site demolition have delayed AAFES (NAF) project execution.

## (6) Cost and Scope Change
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
Notification of Prior Years Construction Cost Increase or Deviation in Scope Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0). The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoD Facility Analysis Category Code. Please make sure to use the 4 digit code.
Number of Projects | Component | FY Approved | State / Country | Installation (1) | Installation Code (2) | Project Title | Project Number (3) | DoD FAC Code (4) | Approved Construction Cost ($000) | Approved Cost Scope | Approved Cost Scope Type | New Construction ($000) | New Construction Scope | New Construction Scope Type | Rationale for Cost / Scope Change
*** A summary paragraph shall be provided describing the rationale for each cost/scope change project. ****
Fort George G Meade, MD, Pet Care Center
The Fort Meade Pet Care Center is being re-reported as a cost increase of more than 25 percent caused by inflation due to project delays from the initial FY17 approval.
Delays were caused by: 1) Failed attempt to incorporate the scope of one of the fire damaged pet care facilities under the same contract. The facility was not able to be
restored and had to be demolished and the 2) Due to the COVID 19 pandemic the State of Maryland's Division of Environmental has experienced slower than normal processing
times for our Storm Water Pollution Prevention Permit. After a long wait, we finally received this permit on 4 June 2021 allowing us to proceed with the project.
Fort Hood, TX, Recreational Cabins
This project is being re-reported due to a cost increase of $6.8M due to deficiencies within the public utility infrastructure. The increase will fix the issues within
the utility lines and fix the infrastructure shortfall.
Joint Base Lewis-McChord, WA, Recreational Vehicle Park
Project added back in the features the Value Engineering Study originally removed at the direction of the IMCOM Director for Readiness thus increasing the cost of the
project.
U.S. Army Garrison Baumholder, Germany, Army Lodging Facility (Replacement)
The original cost from the Project Validation Assessment (PVA) contractor did not take in consideration many of the standard design requirements. A forensic cost
comparison study was conducted using the FY21 Hoenfels Lodge as a benchmark revealed the cost deviations between the two facilities. The Hoenfels Lodge has 82 rooms
verses the Baumholder Lodge at 78 rooms. Since Army Lodges have standard design features, it was decided that the cost per square foot should be more aligned with the
Hoenfels Lodge. The cost from the A&E’s 65% design was used to make the adjustment resulting in a cost deviation greater than 25%.
*** A summary paragraph shall be provided describing the rationale for each cost/scope change project. ****

## (7) MILCON
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed Construction
Military Construction (MILCON) Appropriation Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell.
Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoD Facility Analysis Category Code. Please make sure to use the 4 digit code.
Number of Projects | Component | State / Country | Installation (1) | Installation Code (2) | Project Title | Project Number (3) | DoD FAC Code (4) | Project Cost ($000)
1 | [7 empty] | 0
2 | [7 empty] | 0
3 | [7 empty] | 0
4 | [7 empty] | 0
5 | [7 empty] | 0
6 | [7 empty] | 0
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0

## (8) Public-Private Ventures
ENCLOSURE 5
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
FY 2024 Proposed Public Private Venture Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0).
The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation Code corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoD Facility Analysis Category Code. Please make sure to use the 4 digit code.
Number of Projects | Component | State / Country | Original Program Year | Installation (1) | Installation Code (2) | Project Number (3) | Project Title | DoD FAC Code (4) | Proposed Cost Avoidance ($000)
1 | [8 empty] | 0
2 | [8 empty] | 0
3 | [8 empty] | 0
4 | [8 empty] | 0
5 | [8 empty] | 0
6 | [8 empty] | 0
7 | [8 empty] | 0
8 | [8 empty] | 0
9 | [8 empty] | 0
10 | [8 empty] | 0
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
FY 2022 Cancelled Public Private Venture Summary Data
Number of Projects | Component | State / Country | Original Program Year | Installation (1) | Installation Code (2) | Project Number (3) | Project Title | DoD FAC Code (4) | Proposed Cost Avoidance ($000)
1
2
3
4
5
6
7
8
9
10

## (9) Enhanced Use Lease Summary
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed
Enhanced Use Lease Projects Summary Data
Number of Projects | Component | Program Year | State / Country | Installation | Installation Code | Leasing Entity | Total Value ($000)
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0

## (10) Status of Major Projects
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed Construction
Status of Previously Approved Major Construction Projects
Status of Previously Approved Major Construction Projects Summary Data
Note:
(1) | Please search for the Installation name within the (0) NAFSGL Installation List tab. This will allow you to quickly filter by specific Service and Location.
We recommend copying the Installation name directly into the cell. Please use the name Placeholder if you do not find an Installation name that fits your specific needs.
If using Placeholder, please provide background information within the "Feedback & Comments" table on Tab (0). The NAFSGL Installation List has been agreed upon by the Services and signed into policy.
Installation List has been agreed upon by the Services and signed into policy.
(2) | Input Installation ID in combination with Installation Code as an alphanumeric entry corresponding to Installation name found within the (0) NAFSGL Installation List Tab.
(3) | Input project number from DD Form 1391, Block 7.
(4) | Input DoD Facility Analysis Category Code. Please make sure to use the 4 digit code.
(5) | Only report actual dates. Otherwise, please leave blank.
(6) | Once projects have completed their post validation assessment and have been briefed to OSD they no longer need to be reported on this form.
Number of Projects | Component | FY Approved | State / Country | Installation | Installation Code (2) | Project Title | Project Number (3) | DoD FAC Code (4) | Initial Approved Total Investment ($000) | Current Approved Total Investment ($000) | Initial Approved Project Scope | Initial Approved Project Scope Type | Current Approved Project Scope | Current Approved Project Scope Type | Contract Award Date (MM/DD/YY) (5) | Actual Cost to Date ($000) | Estimated Total Cost to Completion ($000) | Actual Completion Date (MM/DD/YY) (5) | Funding | Actual Date Post Occupancy Review Completed (MM/DD/YY) (5, 6) | Projected Total Cost | Notes

## (11) FY24 Capital Investment
Department of Defense
Commissary Surcharge, Nonappropriated Fund, and Privately Financed Construction
Annual Capital Investment Programs Summary Data (As of May 16th, 2023)
($000s)
Note: - Please populate cells that are shaded light blue. - Update cells shaded light purple as needed
Service Programs |  | Year -3 (2020) | Year -2 (2021) | Year -1 (2022) | Current Year (2023) | Program Year (2024) | Program Year +1 (2025)
Army Lodging
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furniture, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Army Civilian MWR
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furniture, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Army Military MWR
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furniture, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Army Supplemental Mission
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furniture, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
NAVY Exchange
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
NAVY Military MWR
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
NAVY Civilian MWR
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0
Major and Minor Construction
All Other Facility Investment
| Furnitures, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
NAVY (NEXCOM) (PCS) Lodging
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
NAVY (TDY) Lodging
Facilities and Improvements
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
NAVY Supplemental Mission
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
MCCS Exchange
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
MCCS Military MWR
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
USMC Civilian MWR
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0
Major and Minor Construction
All Other Facility Investment
| Furnitures, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
MCCS Lodging
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
USMC Supplemental Mission
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Air Force Military MWR
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Air Force Civilian MWR
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Air Force Lodging
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Air Force Supplemental Mission
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Army Air Force Exchange Service
Facilities and Improvements (Land and Structures)
Major and Minor Construction
All Other Facility Investment
Furniture, Fixtures and Equipment
Information Technology
| AAFES Total | 0 | 0 | 0 | 0 | 0 | 0
Defense Commissary Agency DeCA
Facilities and Improvements (Land and Structures) *
Major and Minor Construction
All Other Facility Investment
Furnitures, Fixtures and Equipment
Information Technology
| Sub Total | 0 | 0 | 0 | 0 | 0 | 0
Equipment Maintenance/Lease/Rents (Not included above)
| DeCA Grand Total | 0 | 0 | 0 | 0 | 0 | 0
TOTAL
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
| Furniture, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Grand Total | 0 | 0 | 0 | 0 | 0 | 0
Exchanges (NEXCOM, MCX, AAFES)
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Exchange Total | 0 | 0 | 0 | 0 | 0 | 0
Military MWR
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Military MWR Total | 0 | 0 | 0 | 0 | 0 | 0
Civilian MWR
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Civilian MWR Total | 0 | 0 | 0 | 0 | 0 | 0
Lodging
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Lodging Total | 0 | 0 | 0 | 0 | 0 | 0
Supplemental Mission
| Facilities and Improvements (Land and Structures) | 0 | 0 | 0 | 0 | 0 | 0
Major and Minor Construction
All Other Facility Investment
| Furniture, Fixtures and Equipment | 0 | 0 | 0 | 0 | 0 | 0
| Information Technology | 0 | 0 | 0 | 0 | 0 | 0
| Supplemental Mission Total | 0 | 0 | 0 | 0 | 0 | 0

## (12) 5 Year Funding Report
5 Year Funding Summary Data (FY 2024 - 2028)
Commissary Surcharge, Nonappropriated Fund & Privately Financed Construction Program
($ Millions)
Note: - Please populate cells that are shaded light blue.
Total Shortfall | 0
Army MWR Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Army Lodge Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
AAFES Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Navy MWR Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Navy Gateway Inns & Suites (TDY Lodging) Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Navy Lodge (PCS Lodging) Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Navy Exhange (NEX) Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
MCCS MWR/Lodging/Exchange Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Air Force MWR Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
Air Force Lodging Shortfall | 0
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
NAF Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0
DeCA Shortfall
($M)
FY | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Capital Requirement | [5 empty] | 0
Surcharge Available | [5 empty] | 0
Delta | 0 | 0 | 0 | 0 | 0 | 0